**From:** Poundcake/ Doyle 13

**To:** Mart Doyle

**Subject:** Weekly Progress Report – November 4, 2016

**Period:** 10/28/16-11/04/16

**Hours:** 8H**ours to Date:** 42

**Accomplishments for *November 4*, 2016**

1. Provided our entrepreneurs with another list of possible freelance web developers to choose from and stay within budget of $3000.
2. Set date for video shoot where they are displaying a sample of their makeup.

**Goals for *November 11*, 2016**

1. Decide and move forward with the web developer they want.
2. Meet with team to discuss how and where to use the video that will be produced.

**Issues:**

1. We are more behind schedule than we thought with finding a developer.