## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-09
Project Name: | Along The Way | [5 empty] | Project Status: | G
Project Description: | Finding local festivals, concerts, fairs and other activities that don’t have widespread advertising and usually only locals would know about is a problem that people have when looking for these events. By using this app people will be able to find smaller festivals, concerts and events within a single app instead of having to search multiple websites for local activities taking place in that particular area.
Customer | Smartphone Users
Project Core Team: | Justin Klaugh, Theo Wilks, James Dantonio, Michael Seagraves
Next Milestone: | Implement a website
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-04-12 | Testing | G | 2016-04-07
Design | Y | 2016-04-07 | Installation | G | 2016-04-07
Construction | G | 2016-04-07
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week, we completed the project charter, assigned roles, assigned completion dates, and established the potential customer base.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2016-01-26 | 2016-01-26 |  | 2016-02-29
Project Charter | G | Design |  | 2016-01-26 | 2016-01-26 |  | 2016-02-29
Final project plan | Y | Analysis |  | 2016-03-01 |  |  | 2016-04-07
UI Mockup | G | Design
--- User login | G | Design |  | 2016-03-01 |  |  | 2016-04-07
--- Account maintenance | G | Design |  | 2016-03-01 |  |  | 2016-04-07
--- Event maintenance | G | Design |  | 2016-03-01 |  |  | 2016-04-07
--- Search events | G | Design |  | 2016-03-08 |  |  | 2016-04-07
--- Event reminders | G | Design |  | 2016-03-08 |  |  | 2016-04-07
--- Add events | G | Design |  | 2016-03-08 |  |  | 2016-04-07
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
Next week we have our website up and running. We will also revise our project charter.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.