## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-22
Project Name: | Along The Way | [5 empty] | Project Status: | G
Project Description: | Finding local festivals, concerts, fairs and other activities that don’t have widespread advertising and usually only locals would know about is a problem that people have when looking for these events. By using this app people will be able to find smaller festivals, concerts and events within a single app instead of having to search multiple websites for local activities taking place in that particular area.
0
Customer | Smartphone Users
Project Core Team: | Justin Klaugh, Theo Wilks, James Dantonio, Michael Seagraves
Next Milestone: | Finalizing the app, data models, and project site.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-04-12 | Testing | G | 2016-04-07
Design | Y | 2016-04-07 | Installation | G | 2016-04-07
Construction | Y | 2016-04-07
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Completed rough draft of protoype. Added screenshots and reformatted project site. Started to draft an implementation plan and project deck.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2016-01-26 | 2016-01-26 |  | 2016-02-29
Project Charter | G | Design |  | 2016-01-26 | 2016-01-26 |  | 2016-02-29
Project Site | G | Design |  | 2016-02-02 | 2016-02-02 |  | 2016-04-07
Final project plan | Y | Analysis |  | 2016-03-01 | 2016-02-17 |  | 2016-04-07
UI Mockup | G | Design
--- User login | G | Design |  | 2016-03-01 |  |  | 2016-04-07
--- Account maintenance | G | Design |  | 2016-03-01 | 2016-02-17 |  | 2016-04-07
--- Event maintenance | G | Design |  | 2016-03-01 | 2016-02-17 |  | 2016-04-07
--- Search events | G | Design |  | 2016-03-08 | 2016-02-17 |  | 2016-04-07
--- Favorite events | G | Design |  | 2016-03-08 |  |  | 2016-04-07
--- Add events | G | Design |  | 2016-03-08 | 2016-02-17 |  | 2016-04-07
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
We plan to have a final version of the prototype by the second week of April. We plan to figure out the financials and systems architecture of our project by the first week of April. We plan to polish up our project deck within the next week.
Note on B47: Key Issues are issues that need your CM Director-level understanding and awareness.