## Sheet1
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date:
Project Name: | Anti-Aggretor | [5 empty] | Project Status: | Y
Project Description: | Create consumer insight into personal data collection and frequency byt third parties
Customer | Anyone with an electronic footprint
Project Core Team: | Mike McAleer, Ryan Boyce, Steve Martorelli, Jim Long, Will Cummings
Next Milestone: | Delivery of Prototype and first version of presentation
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2015-01-21 | Testing | Y | 2015-03-31 |  | G
Design | G | 2015-01-27 | Installation | Y | 2015-03-31
Construction | Y | 2015-02-03
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Decision has been reached on functionality of app and prototyping has begun, meeting with Ben Hasan went very well,
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Brainstorming | G | Design |  | 2015-01-21 | 2015-01-21 |  | 2005-02-15 | 2005-02-15
Final project plan | Y | Analysis |  | 2005-12-01 | 2005-12-01 |  | 2005-12-15 | 2005-01-10
UI Mockup | G | Design
--- User login | Y | Design |  | 2005-01-15 | 2005-01-20 |  | 2005-01-22 | 2005-01-22
Dashboard | Y |  | Design
--- Data Broker View | Y | Design |  | 2005-02-01 | 2005-02-01 |  | 2005-02-03 | 2005-02-03
--- Defense options | Y | Design |  | 2005-02-01 | 2005-02-01 |  | 2005-02-05 | 2005-02-05
Presentation format | G | Implementation |  | 2015-03-24 | 2015-03-24 |  | 2015-03-24 | 2015-03-24
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Availability of team members |  | Y |  |  |  |  | All team members
R
Planned Accomplishments
Have working prototype available
Note on B45: Key Issues are issues that need your CM Director-level understanding and awareness.