## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-03-16
Project Name: | Implement Effective Barbershop Appointment Scheduling | [5 empty] | Project Status: | G
Project Description: | Service providers work directly with their customers. Whether it’s a nail salon or a barber shop the providers rely directly on their customers scheduling appointments with them. Initially, providers are at the mercy of their customers. When a customer calls or texts for an appointment, it initiates a back and forth conversation to iron out the exact time and date. We look to eliminate that problem and allow our providers to utilize their time more effectively in growing their business rather than scheduling appointments. Providers will be able to add a scheduling platform to their website that customers will be able to view the providers schedule and make an appointment with them at their convenience.
Customer | Service Providers: barbers, auto technicians, nail salons, etc.
Project Core Team: | Alisa Islam; Jacob A Andrews; Shane Fowler; Shuyue Ding
Next Milestone: | Complete Design phase
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-02-03 | Testing | G | 2018-04-04
Design | Y | 2018-02-26 | Installation | G | 2018-04-24
Construction | G | 2018-03-30
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
1. First mentor meeting; 2. Researched cost and forecasted profit; 3. Continued to add on more providers to test out the scalability of the prototype 4. Exploring options to monetize the prototype
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Updated Project Charter | G | Design |  | 2018-01-31 | 2018-01-31 |  | 2018-01-31 | 2018-01-31
Overall planning | G | Analysis |  | 2018-02-05 | 2018-02-05 |  | 2018-02-05 | 2018-02-05
Business case | G | Documentation |  | 2018-03-15 | 2018-03-15 |  | 2018-03-16 | 2018-03-16
Project Deck | G | Documentation |  | 2018-03-15 | 2018-03-15 |  | 2018-03-16 | 2018-03-16
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Contact with mentor |  | Y | Set up meeting and send deliverables to mentor
Planned Accomplishments
1. Update Enterprise Architecture, data model, and business diagram; 2. Create group project site