## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-03-29
Project Name: | Implement Effective Barbershop Appointment Scheduling | [5 empty] | Project Status: | G
Project Description: | Service providers work directly with their customers. Whether it’s a nail salon or a barber shop the providers rely directly on their customers scheduling appointments with them. Initially, providers are at the mercy of their customers. When a customer calls or texts for an appointment, it initiates a back and forth conversation to iron out the exact time and date. We look to eliminate that problem and allow our providers to utilize their time more effectively in growing their business rather than scheduling appointments. Providers will be able to add a scheduling platform to their website that customers will be able to view the providers schedule and make an appointment with them at their convenience.
Customer | Service Providers: barbers, auto technicians, nail salons, etc.
Project Core Team: | Alisa Islam; Jacob A Andrews; Shane Fowler; Shuyue Ding
Next Milestone: | Complete Design phase
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-02-03 | Testing | G | 2018-04-04
Design | Y | 2018-02-26 | Installation | G | 2018-04-24
Construction | G | 2018-03-30
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
1. Fixed Business Process model to include cancellation process 2. Updated systems architecture design 2. Updated data model with correct cardinalities
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Updated Project Charter | G | Design |  | 2018-01-31 | 2018-01-31 |  | 2018-01-31 | 2018-01-31
Overall planning | G | Analysis |  | 2018-02-05 | 2018-02-05 |  | 2018-02-05 | 2018-02-05
Business case | G | Documentation |  | 2018-03-15 | 2018-03-15 |  | 2018-03-16 | 2018-03-16
Project Deck | G | Documentation |  | 2018-03-15 | 2018-03-15 |  | 2018-03-16 | 2018-03-16
Update process model and systems architecture design | G | Documentation |  | 2018-04-09 | 2018-04-09 |  | 2018-04-09 | 2018-04-09
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
We don't have our theme yet for the project site, we only have the information on the standard site template |  | Y | Get our template for our project site and then Alisa will update the website with all of our information |  |  |  | Alisa
Planned Accomplishments
1.Work on our business case and update our financials
Note on B49: Key Issues are issues that need your CM Director-level understanding and awareness.