## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-10-03
Project Name: | Combating credit card fraud | [5 empty] | Project Status: | Y
Project Description: | In 2014, 31.8 Million US consumers had their credit cards breached resulting in $16 billion dollars in losses, more than three times the number affected in the previous year. In fact, the U.S. is responsible for 47% of the worlds card fraud which totals $5.55 Billion. About 90% of card breach victims in 2014 required replacement cards, which totaled as much as $12.75 per card in some cases. As people continue to use electronic forms of payment, especially for high price items, fraud and credit card theft will only continue to grow. This project will allow card holders to become an active member in the fight against theft and help them better control their financial health. By utilizing a simple mobile application card members will be able to pre-approve large purchases and alert their financial institutions when they are making purchases outside of their usual location. This will result in a lower amount of time and money spent halting transactions and investigating purchases. This will also help to improve the card holder’s credit score.
Customer | Sebastion Brown, Senior Manager, US Banks
Project Core Team: | Trevor Johnson, Chris Montone, Yebin Seo
Next Milestone: | Requirements gathering and application design
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-28 | Testing | Y | 2016-11-23
Design | G | 2016-10-12 | Installation | Y | 2016-11-26
Construction | G | 2016-10-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Last week we began prototyping the "Approve Purchase" function within our application. We also met to discuss the valuation of our application.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Application idea development | G | Design |  | 2016-08-30 | 2016-08-30 | Key Features decided | 2016-10-10 | 2016-10-12
Prototyping | G | Design |  | 2016-10-12 | 2016-10-12 |  | 2016-11-20
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Behind in deciding on the key features |  | G | We have decided on the key features of our application |  |  |  | Team
Planned Accomplishments
We plan to further develop our prototype and begin to look at how we can measure success for our project.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.