## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-11-01
Project Name: | ApproveIT | [5 empty] | Project Status: | Y
Project Description: | In 2014, 31.8 million U.S. consumers lost $16 billion by having their credit cards breached. This resulted in a total of $16 billion in losses which is more than three times the number affected in 2013. In fact, the U.S. is responsible for 47% of the world's credit card fraud which totals $5.55 billion. In 2014, about 90% of card breach victims required replacement cards, which totaled as much as $12.75 per card. As people continue to use electronic forms of payment, especially for high price items, fraud and credit card theft will only continue to grow. Thus, ApproveIT will allow card holders to become an active member in the fight against theft by allowing them to better control their financial health. By utilizing a simple mobile application, card holders will be able to pre-approve large purchases, and allow them to alert their financial institutions when they are making purchases outside of their usual location. Additionally, the app will allow users to one-click freeze all of their credit cards in the unfortunate cases where all of there cards have been breached. This will result in a lower amount of time and money both consumers and businesses spend when they halt transactions and investigate purchases.
Customer | Sebastion Brown, Senior Manager, US Banks
Project Core Team: | Trevor Johnson, Chris Montone, Yebin Seo
Next Milestone: | Prototype design and website creation
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-09-28 | Testing | G | 2016-11-23
Design | G | 2016-10-12 | Installation | G | 2016-11-26
Construction | Y | 2016-10-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
We discussed the application's value proposition and main features. We also decided on how we will make money from the application. Lastly, we started designing the community website for our application.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Application idea development | G | Analysis/Design |  | 2016-08-30 | 2016-08-30 | Key Features decided | 2016-10-10 | 2016-10-12
Deciding on key features | G | Analysis/Design |  | 2016-08-30 | 2016-08-30 |  | 2016-10-11 | 2016-10-18
Prototyping | Y | Construction |  | 2016-10-12 | 2016-10-12 |  | 2016-11-20
Website creation | Y | Construction |  | 2016-10-25 | 2016-10-25 |  | 2016-11-22
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Behind in deciding on the key features |  | G | We have decided on the key features of our application |  |  |  | Team
Planned Accomplishments
We plan to further develop our prototype for the application and continue to set-up our MIS website.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.