## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-16
Project Name: | Business Analyst Club | [5 empty] | Project Status: | Y
Project Description: | After graduation, a majority of Fox’s MIS students become Business Analysts (BA’s) for consulting firms. In MIS 3504, we support a real client and act as a BA the entire semester. Other than that semester, we get little consulting experience. Our group wants to form a Temple Business Analyst Club, and support local businesses or other Temple affiliated groups. The club will work on small IT related projects, like recreating a company’s webpage, or increasing their online presence. The club will offer students more consulting experience to further their education here at Temple University.
Customer | Small Businesses, Start ups, Temple-addiliated programs
Project Core Team: | Ibtihal Al-Froukh, Samuel McAdoo, David Rivera, Christian Wenner
Next Milestone: | Meeting with AIS President / AIS Approval
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-01-19 | Testing | Y | 2016-03-29
Design | G | 2016-02-23 | Installation | Y | 2016-04-05
Construction | Y | 2016-03-05
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
- Emailed AIS President about the BA Club and whether or not AIS would sponsor us. - Continued working and editing the project website and charter.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter Revision | G | Analysis |  | 2016-02-01 | 2016-02-01 | Still revising | 2016-04-21 | 2016-04-21
Website Layout (draft) | G | Design |  | 2016-02-08 | 2016-02-08 | Still revising | 2016-04-20 | 2016-04-21
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
AIS approval |  | G | Still pending |  |  |  | Chris
Planned Accomplishments
Next week we are hoping to meet with the AIS president and get AIS's approval in regards to our partnership with them. In addition, we are hoping to get faculty support for our project in order to assist us with different aspects of the project and club.
Note on B45: Key Issues are issues that need your CM Director-level understanding and awareness.