## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-07
Project Name: | Business Analyst Club | [5 empty] | Project Status: | Y
Project Description: | After graduation, a majority of Fox’s MIS students become Business Analysts (BA’s) for consulting firms. In MIS 3504, we support a real client and act as a BA the entire semester. Other than that semester, we get little consulting experience. Our group wants to form a Temple Business Analyst Club, and support local businesses or other Temple affiliated groups. The club will work on small IT related projects, like recreating a company’s webpage, or increasing their online presence. The club will offer students more consulting experience to further their education here at Temple University.
Customer | Small Businesses, Start ups, Temple-addiliated programs
Project Core Team: | Ibtihal Al-Froukh, Samuel McAdoo, David Rivera, Christian Wenner
Next Milestone:
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-01-19 | Testing | Y | 2016-03-29
Design | G | 2016-02-23 | Installation | Y | 2016-04-05
Construction | Y | 2016-03-05
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
- Group meeting through WebEx 2/24/16- discussed our goals moving foward and brainstormed ideas for the prototype. - Meeting with AIS president 2/24/16- discussed our project and the need for an SPO partnership to support the BA Club and help spread information. The president liked the idea and will support us. - Completed a draft of the BA website
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter Revision | G | Analysis |  | 2016-02-01 | 2016-02-01 | Still revising | 2016-04-21 | 2016-04-21
Website Layout (draft) | G | Design |  | 2016-02-08 | 2016-02-08 | Still revising | 2016-04-20 | 2016-04-21
Prototype (draft) | Y | Design |  | 2/24-3/6 | 2016-03-07 |  | 2016-03-08 | 2016-03-08
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Prototype draft |  | R | Started later than expected due to busy schedule. It's only the first draft and we will improve it as we go on. |  |  |  | David/Sam
Planned Accomplishments
- Start working with AIS in order to assist us with different aspects of the project and club. - Keep working on and improving the prototype, revise documents, and website - Start working on the project deck slides
Note on B45: Key Issues are issues that need your CM Director-level understanding and awareness.