## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-12
Project Name: | MIS 3545 Data Driven Business Intelligence | [5 empty] | Project Status: | G
Project Description: | After graduation, a majority of Fox’s MIS students become Business Analysts (BA’s) for consulting firms. In MIS 3504, we support a real client and act as a BA the entire semester. Other than that semester, we get little consulting experience. Our group wants to create a Temple MIS Data Driven Business Intelligence Class to allow students to gain experience by working on real world projects. Students will work on small IT related projects that is focused on finding a solution rather than building the solution. By offering students additional consulting experience, it will lead to better prepared graduations which will reflect on the education they received at Temple.
Customer | IBIT Members, Temple-affiliated programs
Project Core Team: | Ibtihal Al-Froukh, Samuel McAdoo, David Rivera, Christian Wenner
Next Milestone:
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-01-19 | Testing | G | 2016-03-29
Design | G | 2016-02-23 | Installation | G | 2016-04-05
Construction | G | 2016-03-05
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
- This week we continued revising necessary deliverables - We discussed and completed our financials for 3 years of the MIS course
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter Revision | G | Analysis |  | 2016-02-01 | 2016-02-01 | Still revising | 2016-04-21 | 2016-04-21
Project Website | G | Design |  | 2016-02-08 | 2016-02-08 | Still revising | 2016-04-20 | 2016-04-21
Prototype | Y | Design |  | 2/24-3/6 | 2016-03-07 | Still revising | 2016-04-20 | 2016-04-20
Project Deck | G | Analysis |  | 2016-04-04 | 2016-04-04 | Majority completed | 2016-04-21 | 2016-04-20
Financials (revision) | G | Analysis |  | 2016-04-05 | 2016-04-12 |  | 2016-04-21 | 2016-04-20
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Plan realignment |  | G | Could delay our project time/deliverables/ We are back on schedule. New plan didn't have major affect on our project |  |  |  | All
Planned Accomplishments
- We plan on meeting to run through our presentation before our scheduled presentation date - Assign parts for each group member to present. - Run through the prototype and make necessary changes to all deliverables
Note on B45: Key Issues are issues that need your CM Director-level understanding and awareness.