## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-05
Project Name: | MIS 3545 Data Driven Business Intelligence | [5 empty] | Project Status: | G
Project Description: | After graduation, a majority of Fox’s MIS students become Business Analysts (BA’s) for consulting firms. In MIS 3504, we support a real client and act as a BA the entire semester. Other than that semester, we get little consulting experience. Our group wants to create a Temple MIS Data Driven Business Intelligence Class to allow students to gain experience by working on real world projects. Students will work on small IT related projects that is focused on finding a solution rather than building the solution. By offering students additional consulting experience, it will lead to better prepared graduations which will reflect on the education they received at Temple.
Customer | IBIT Members, Temple-affiliated programs
Project Core Team: | Ibtihal Al-Froukh, Samuel McAdoo, David Rivera, Christian Wenner
Next Milestone:
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-01-19 | Testing | G | 2016-03-29
Design | G | 2016-02-23 | Installation | G | 2016-04-05
Construction | G | 2016-03-05
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
- This week we updated the prototype, charter, and website - We completed majorty of the project deck slides - We realigned our strategic plan and decided to pursue a MIS course (MIS 3545 Data Driven Business Intelligence) instead of a BA Club. We decided that an MIS elective expanded into an MIS required course will be a better way to address the lack of consulting experience problem FOX students have before they go into their careers. - We discussed the different compenents of the class: first we decided to implement a 1 section elective class the first year. If we have a sufficient amount of registered students, we will add an additional section for the 2nd year. Lastly, we would advance into an MIS required course the 3rd year.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter Revision | G | Analysis |  | 2016-02-01 | 2016-02-01 | Still revising | 2016-04-21 | 2016-04-21
Project website | G | Design |  | 2016-02-08 | 2016-02-08 | Still revising | 2016-04-20 | 2016-04-21
Prototype | Y | Design |  | 2/24-3/6 | 2016-03-07 | Still revising | 2016-04-20 | 2016-04-20
Project Deck | G | Analysis |  | 2016-04-04 | 2016-04-04 | Majority completed | 2016-04-21 | 2016-04-20
Financials | Y | Analysis |  | 2016-04-05 | 2016-04-05 | Need to revise | 2016-04-21 | 2016-04-20
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Plan realignment |  | Y | Could delay our project time/deliverables |  |  |  | All
Financials |  | Y | Needed to revise to reflect new plan
Planned Accomplishments
- Moving forward, we plan on implementing our new plan and focus on producing deliverables to align of our new goals - Make necessary changes to past deliverables to relate to new plan - We plan on having a group meeting to go over the documentations and run through the prototype.
Note on B45: Key Issues are issues that need your CM Director-level understanding and awareness.