## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-05
Project Name: | RateMyRoomie Project | [5 empty] | Project Status: | Y
Project Description: | Finding a roommate, especially if you are new to the area, can be challenging. A roommate is someone you share a living space with and it is very important to find the perfect one. Many people settle on random roommates because of the lack of ease of finding the perfect one and end up in substandard situations. This project will not only make it easier to find a roommate, but match people based on an ideal fit through various personal questions and verifications.
Customer | Anthony Messina, MIS4596, Professor
Project Core Team: | Courtney Kasztelan , Will Black, Loi Tran, Shawn Soto
Next Milestone: | Finish Business Case, Presentation, Competitive Analysis, Data Modeling, Schema and Systems Architecture
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-10 | Testing | G | 2016-04-15
Design | Y | 2016-02-22 | Installation | G | 2004-04-20
Construction | Y | 2016-03-22
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Drafted presentation - Identifying problem, solution, Industry analysis, competitive analysis, High level data model/schema, systems architecture, Financials, budget and implementation plan. Protoype went through its second stage of refining.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Review Idea | G | Analysis |  | 2016-02-10 | 2016-03-15
Final project plan | G | Analysis |  | 2016-02-10 | 2016-03-15
UI Mockup | G | Design |  | 2016-02-22 | 2016-03-15
--- Matching Algorithm | R | Design |  | 2016-02-22 | unk
--- Account maintenance | Y | Design |  | 2016-02-22 | unk | Profile page created |  | 2016-04-04
--- Map API | Y | Design |  | 2016-04-04 | unk
--- Database integration | Y | Design |  | 2016-04-04 | unk
Market Analysis | G | Design |  | 2016-03-05 | unk | Complete |  | 2016-03-24
Competitive Analysis | G | Design |  | 2016-03-05 | unk
Data Schema | G | Design |  | 2016-03-05 | unk
Financials/Budget | G | Analysis |  | 2016-03-28 | unk
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planning Meetings |  | G | Meetings scheduled for every Thursday at 5pm with periodic virtual meetings |  |  |  | All
Time Management |  | Y | Fell behind a little with the schedule, but made up last week with extra meetings |  |  |  | All
Competitive Analysis |  | G | Did a Porter's 5 forces Analysis but still need more information to work with |  |  |  | Shawn
Business Case |  | G | Need to include more analysis |  |  |  | Courtney
Prototype Draft |  | Y | Develop User interface and Customer data input |  |  |  | Loi
Risks & Challenges |  | G | Refining our key risks, updating mitigation plans, and listing key challenges |  |  |  | Will
Planned Accomplishments
Next week our focus will be on finalizing prototype design and start integrating database objects within the User interface. We will continue to update the business case, charter, and manage change to our project scope.
Note on B48: Key Issues are issues that need your CM Director-level understanding and awareness.