## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-10
Project Name: | BestRoomie Project | [5 empty] | Project Status: | G
Project Description: | Finding a roommate, especially if you are new to the area, can be challenging. A roommate is someone you share a living space with and it is very important to find the perfect one. Many people settle on random roommates because of the lack of ease of finding the perfect one and end up in substandard situations. This project will not only make it easier to find a roommate, but match people based on an ideal fit through various personal questions and verifications.
Customer | Anthony Messina, MIS4596, Professor
Project Core Team: | Courtney Kasztelan , Will Black, Loi Tran, Shawn Soto
Next Milestone: | Delivery and Approval of Project Charter
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-10 | Testing | G | 2016-04-15 |  | G | 2016-04-20
Design | G | 2016-02-22 | Installation | G | 2016-04-20
Construction | G | 2016-03-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week we built our project site and completed our project charter.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Review Idea | Y | Analysis |  | 2016-02-10 | unk |  | - | -
Final project plan | Y | Analysis |  | 2016-02-10 | unk |  | - | -
UI Mockup | G | Design |  | 2016-02-22 | unk |  | - | -
--- User login | G | Design |  | 2016-02-22 | unk |  | - | -
--- Account maintenance | G | Design |  | 2016-02-22 | unk |  | - | -
--- Matching Alogirithm | G | Design |  | 2016-02-22 | unk |  | - | -
--- Apartmnet Browser | G | Design |  | 2016-02-22 | unk |  | - | -
--- Roomate Compatibility | G | Design |  | 2016-02-22 | unk |  | - | -
--- Roomate Review | G | Design |  | 2016-02-22 | unk |  | - | -
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planning Meetings |  | Y | Plan Meetings for the project (Hangout, Physical, Hangout, Webex) |  |  |  | Courtney
Planned Accomplishments
Next week we are meeting with to finalize the scope document and the analysis phase of our project. This includes: 1) finalizing the idea and value proposition for the project, 2) Assigning Roles and Responsibilities, 3) Identifying Risks, 4) Draft Work Breakdown Structure
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.