## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-15
Project Name: | RateMyRoomie Project | [5 empty] | Project Status: | Y
Project Description: | Finding a roommate, especially if you are new to the area, can be challenging. A roommate is someone you share a living space with and it is very important to find the perfect one. Many people settle on random roommates because of the lack of ease of finding the perfect one and end up in substandard situations. This project will not only make it easier to find a roommate, but match people based on an ideal fit through various personal questions and verifications.
Customer | Anthony Messina, MIS4596, Professor
Project Core Team: | Courtney Kasztelan , Will Black, Loi Tran, Shawn Soto
Next Milestone: | Finish data model and process model.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-10 | Testing | G | 2016-04-15
Design | Y | 2016-02-22 | Installation | G | 2004-04-20
Construction | Y | 2016-03-22
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Established business model and revenue stream, created data schema.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Review Idea | G | Analysis |  | 2016-02-10 | 2016-03-15
Final project plan | Y | Analysis |  | 2016-02-10 | 2016-03-15
UI Mockup | G | Design |  | 2016-02-22 | 2016-03-15
--- Matching Algorithm | Y | Design |  | 2016-02-22 | unk
--- Account maintenance | Y | Design |  | 2016-02-22 | unk
Market Analysis | Y | Design |  | 2016-03-05 | unk
Competitive Analysis | G | Design |  | 2016-03-05 | unk
Data Schema | G | Design |  | 2016-03-05 | unk
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planning Meetings |  | G | Meetings scheduled for every Thursday at 5pm with periodic virtual meetings |  |  |  | All
Time Management |  | Y | Fell behind a little with the schedule, but made up last week with extra meetings |  |  |  | All
Competitive Analysis |  | Y | Did a Porter's 5 forces Analysis but still need more information to work with |  |  |  | Shawn
Business Case |  | Y | Need to include more analysis |  |  |  | Courtney
Prototype Draft |  | Y | Develop User interface and Customer data input |  |  |  | Loi
Risks & Challenges |  | Y | Refining our key risks, updating mitigation plans, and listing key challenges |  |  |  | Will
Planned Accomplishments
Next week we will complete our market analysis so we can implement our findings within our prototype design. We will build more of our prototype and have the general layout complete. We will be sure to focus on all problems and risks within our project as we work through the prototype while establishing the risks involved after the project is complete.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.