## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-08
Project Name: | BestRoomie Project | [5 empty] | Project Status: | Y
Project Description: | Finding a roommate, especially if you are new to the area, can be challenging. A roommate is someone you share a living space with and it is very important to find the perfect one. Many people settle on random roommates because of the lack of ease of finding the perfect one and end up in substandard situations. This project will not only make it easier to find a roommate, but match people based on an ideal fit through various personal questions and verifications.
Customer | Anthony Messina, MIS4596, Professor
Project Core Team: | Courtney Kasztelan , Will Black, Loi Tran, Shawn Soto
Next Milestone: | UI Mockup / Initial Design Brainstorming
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-10 | Testing | G | 2016-04-15 |  | G | 2016-04-20
Design | Y | 2016-02-22 | Installation | G | 2016-04-20
Construction | G | 2016-03-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Draft Prototype loaded to the Project Site.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Review Idea | G | Analysis |  | 2016-02-10 | unk |  | - | -
Final project plan | G | Analysis |  | 2016-02-10 | unk |  | - | -
UI Mockup | Y | Design |  | 2016-02-22 | unk |  | - | -
--- User login | Y | Design |  | 2016-02-22 | unk |  | - | -
--- Account maintenance | Y | Design |  | 2016-02-22 | unk |  | - | -
--- Matching Alogirithm | Y | Design |  | 2016-02-22 | unk |  | - | -
--- Apartmnet Browser | Y | Design |  | 2016-02-22 | unk |  | - | -
--- Roomate Compatibility | Y | Design |  | 2016-02-22 | unk |  | - | -
--- Roomate Review | Y | Design |  | 2016-02-22 | unk |  | - | -
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planning Meetings |  | G | Meetings scheduled for every Thursday at 5pm with periodic virtual meetings |  |  |  | All
Data Algorithm for roomate matching |  | Y | Open Source research to find and refine working code |  |  |  | Loi
Market Research & Conditions |  | Y | Currently conducting research on market forces |  |  |  | Courtney & Shawn
Risks & Challenges |  | Y | Refining our key risks, updating mitigation plans, and listing key challenges |  |  |  | Will
Prototype Draft |  | Y | Develop User interface and Customer data input |  |  |  | Loi
Planned Accomplishments
Next week we are meeting with to discuss initial design of the prototype. The focus will be split on the matching algorithm for the application and the research and development of market conditions and competitive forces. We will focus on finding open source code to provide proof of concept but also to help with the data modeling in the coming weeks. Additionally, we will begin refining our key risks, updating mitigation plans, and listing key challenges.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.