## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-11
Project Name: | RateMyRoomie Project | [5 empty] | Project Status: | G
Project Description: | Finding a roommate, especially if you are new to the area, can be challenging. A roommate is someone you share a living space with and it is very important to find the perfect one. Many people settle on random roommates because of the lack of ease of finding the perfect one and end up in substandard situations. This project will not only make it easier to find a roommate, but match people based on an ideal fit through various personal questions and verifications.
Customer | Anthony Messina, MIS4596, Professor
Project Core Team: | Courtney Kasztelan , Will Black, Loi Tran, Shawn Soto
Next Milestone: | Complete project and project presentation
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-10 | Testing | G | 2016-04-15
Design | G | 2016-02-22 | Installation | G | 2004-04-20
Construction | Y | 2016-03-22
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Modified presentation, financials, budget and implementation plan. Protoype is 90% done and ready for finalizing.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Review Idea | G | Analysis |  | 2016-02-10 | 2016-03-15
Final project plan | G | Analysis |  | 2016-02-10 | 2016-03-15
UI Mockup | G | Design |  | 2016-02-22 | 2016-03-15
--- Matching Algorithm | R | Design |  | 2016-02-22 | unk | Concept is down, but not implementation
--- Account maintenance | Y | Design |  | 2016-02-22 | unk | Profile page created |  | 2016-04-04
--- Map API | Y | Design |  | 2016-04-04 | unk
--- Database integration | Y | Design |  | 2016-04-04 | unk
Market Analysis | G | Design |  | 2016-03-05 | unk | Complete |  | 2016-03-24
Competitive Analysis | G | Design |  | 2016-03-05 | unk | Complete
Data Schema | G | Design |  | 2016-03-05 | unk | Complete
Financials/Budget | G | Analysis |  | 2016-03-28 | unk | Still in progress
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planning Meetings |  | G | Meetings scheduled for every Thursday at 5pm with periodic virtual meetings |  |  |  | All
Time Management |  | Y | Only have 1 week left, so we have to cram a lot of work in a short amount of time |  |  |  | All
Documentation Organization |  | Y | Have a lot of documentation that still needs to be finalized and organized |  |  |  | Shawn
Business Case |  | G | Need to refine the financials and visuals of the business case |  |  |  | Courtney
Prototype Completion |  | G | 90% finished. Have 1 week to complete |  |  |  | Loi
Risks & Challenges |  | G | Refining our key risks, updating mitigation plans, and listing key challenges |  |  |  | Will
Planned Accomplishments
Next week, we will finalize our entire project. Finish the prototype, business case, documentation, and powerpoint.
Note on B48: Key Issues are issues that need your CM Director-level understanding and awareness.