## Status Summary
Project Dashboard
| Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-02-19
| Project Name: | Book Broker | [5 empty] | Project Status: | G
| Project Description: | College students do not have a centralized system of exchanging and selling book products. Students often look to post books on websites like ebay, facebook, amazon, offerup to sell/buy books. This process is not efficient as it does not revolve around any particular universities.
| Customer | Robert Smith, College Student, Temple University
| Project Core Team: | Angie Wang Tim McNiff Jurgen Aliaj Frank Tkachenko
| Next Milestone: | Build Business Requirments
Phase Status
|  | Status | Plan |  | Status | Plan |  | Status | Date
| Analysis | G | 2018-02-01 | Testing | G | 2018-03-03
| Design | G | 2018-02-07 | Installation | G | 2018-04-15
| Construction | G | 2018-02-15
| Leading Indicators | Status |  |  | Status |  |  | Status
| On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We worked on the proccess model, data model, system architecture diagram, and deck. We also discussed the how the application will work and features that we want it to have.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
[5 empty] | START |  |  | END
| Current Key Activities | STATUS | PHASE |  | PLAN | ACT | Comments | PLAN | ACT
| Project Charter | G | Planning |  | 2018-01-29 |  |  | 2018-03-20
| Business Case | G | Planning |  | 2018-02-01 | 2005-02-01 |  | 2005-02-15
Bui | Business Requirements | G | Analysis |  | 2018-02-04 |  |  | 2005-02-16
| System Architech Diagram | G | Analysis |  | 2018-03-03 |  |  | 2005-02-17
| Process Model | G | Analysis |  | 2018-03-10 |  |  | 2005-02-18
| Final project plan | G | Analysis |  | 2005-12-01 |  |  | 2005-12-15
| UI Mockup | G | Design |  | 2018-02-01 |  |  | 2005-12-16
| --- User login | G | Design |  | 2018-02-04 |  |  | 2018-02-08
| --- Filter Universities | G | Design |  | 2018-02-05 |  |  | 2018-02-09
| --- Search Function | G | Design |  | 2018-02-06 |  |  | 2018-02-10
| --- Catalog maintenance | G | Design |  | 2018-02-07 |  |  | 2018-02-11
| --- Browse catalog | G | Design |  | 2018-02-08 |  |  | 2018-02-12
| --- Add to shopping cart | G | Design |  | 2005-02-09 |  |  | 2018-02-13
| Testing | G | Implementation |  | 2018-03-03 |  |  | 2018-02-14
| Deployment | G | Installation |  | 2018-04-15 |  |  | 2018-02-15
Key Issues
| Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
Next week, we will revise the process model, data model, and system architecture diagram after discussing it all together.