## Status Summary
Project Dashboard
| Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-03-26
| Project Name: | Book Broker | [5 empty] | Project Status: | G
| Project Description: | College students do not have a centralized system of exchanging and selling book products. Students often look to post books on websites like ebay, facebook, amazon, offerup to sell/buy books. This process is not efficient as it does not revolve around any particular universities.
| Customer | Robert Smith, College Student, Temple University
| Project Core Team: | Angie Wang Tim McNiff Jurgen Aliaj Frank Tkachenko
| Next Milestone: | Build Business Requirments
Phase Status
|  | Status | Plan |  | Status | Plan |  | Status | Date
| Analysis | G | 2018-02-01 | Testing | G | 2018-04-06
| Design | G | 2018-03-17 | Installation | G | 2018-04-15
| Construction | G | 2018-03-18
| Leading Indicators | Status |  |  | Status |  |  | Status
| On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Met with our mentor and he gave us suggestions on our project. We also updated our proccess model, data model, system architecture. Continued working on the prototype and created a techinical architecture. We also added all updated documents to our community site - http://community.mis.temple.edu/bookbroker/
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
[5 empty] | START |  |  | END
| Current Key Activities | STATUS | PHASE |  | PLAN | ACT | Comments | PLAN | ACT
| Project Charter | G | Planning |  | 2018-01-29 | 2018-01-29 | Updated Charter | 2018-03-20 | 2018-03-18
| Business Case | G | Planning |  | 2018-02-01 | 2018-03-16 |  | 2005-02-15
Bui | Business Requirements | G | Analysis |  | 2018-02-04 | 2018-01-29 |  | 2005-02-16
| System Architech Diagram | G | Analysis |  | 2018-03-03 | 2018-02-19 | Updated Systems Arch | 2018-03-26 | 2018-03-26
| Process Model | G | Analysis |  | 2018-03-10 | 2018-02-19 | Updated Process Model | 2018-03-26 | 2018-03-27
| Final project plan | G | Analysis |  | 2005-12-01 | 2018-03-18 |  | 2005-12-15
| UI Mockup | G | Design |  | 2018-02-01 | 2018-03-18 |  | 2005-12-16
| --- User login | G | Design |  | 2018-02-04 | 2018-03-19 |  | 2018-02-08
| --- Filter Universities | G | Design |  | 2018-02-05 | 2018-03-20 |  | 2018-02-09
| --- Search Function | G | Design |  | 2018-02-06 | 2018-03-21 |  | 2018-02-10
| --- Catalog maintenance | G | Design |  | 2018-02-07 | 2018-03-26 |  | 2018-02-11
| --- Browse catalog | G | Design |  | 2018-02-08 | 2018-03-27 |  | 2018-02-12
| --- Add to shopping cart | G | Design |  | 2005-02-09 | 2018-03-28 |  | 2018-02-13
| Testing | G | Implementation |  | 2018-03-03 | 2018-04-06 |  | 2018-02-14
| Deployment | G | Installation |  | 2018-04-15 | 2018-04-17 |  | 2018-02-15
Key Issues
| Description |  | Status | Resolution/Update |  |  |  | Owner
| Obtaining user base |  | G | Make the app easy to use and specified for universities - making it different from Facebook, OfferUp, etc. |  |  |  | Tim McNiff, Frank Tkachenko
| The app is functioning during dry run of presenation - so we can demo it. |  | G | Make sure we stay on schedule with prototype development |  |  |  | Tim McNiff, Frank Tkachenko, Angie
Planned Accomplishments
Continue to work on prototype and project community site. Meeting with our mentor again on April 3, 2018 @ 7/8pm Update competitive analysis, market segmentation. Work on putting together final presentation slides.