## Sheet1
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-07
Project Name: | BookzBrothers App and Website Implementation | [5 empty] | Project Status: | G
Project Description: | The Temple University Facebook group is flooded with hundreds of posts from students attempting to sell and buy textbooks. Very few students are successful in filtering through these posts to find the right book and price. This project will improve the process and efficiency of buying and selling textbooks among students. Students will be able to search books available by school, major, course, professor, and book condition on the application and/or website. We will have each new member create a login. Students will pay a minimal fee to become a member of the website for six months (a semester). The student will be able to pay this fee with a debit or credit card.
Customer | Tony Messina
Project Core Team: | Bridgette Weirch Karan Patel Piya Mewa Troy Gillispie Dave Gubitosa
Next Milestone: | Delivery of 1st phase of prototypes
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-01 | Testing | G | 2016-02-17
Design | G | 2016-02-11 | Installation | G | 2016-02-20
Construction | G | 2016-02-11
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We have a foundation for our mobile and website prototypes. We have all visuals and displays of the features it will include.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Community Site | G | Design |  | 2016-02-01 | 2016-02-03 |  | 2016-02-03 | 2016-02-10
Final project plan | G | Analysis |  | 2016-02-01 | 2016-02-10 |  | 2016-02-10 | 2016-02-10
App/Website Mockup | G | Design
--- User login | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20
--- Account maintenance | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20
--- Catalog maintenance | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20
--- Browse catalog | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20
--- Add to shopping cart | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20
--- Receive contact information | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Challenges |  | Y | Figure out how to access all colleges' course IDs and related info |  |  |  | Bridgette
Challenges |  | Y | Figure out how to attract and sustain customer base |  |  |  | Piya
Risk |  | Y | List out potential risks associated with protoypes in regards to customer data |  |  |  | Troy
Market |  | Y | Need to analyze and define how to differentiate ourselves from similar apps and websites |  |  |  | Dave
Research |  | Y | Need to figure out how to remain profitable and have customers willing to pay |  |  |  | Karan
Planned Accomplishments
We are meeting as a group to go over the protypes and to make sure they are compatible and serve the same function. We will discuss and find solutions to the above key issues. We will meet with the metor who will help us assess our progress and assit in moving forward.