## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-29
Project Name: | BookzBrotherz App and Website Implementation | [5 empty] | Project Status: | G
Project Description: | The Temple University Facebook group is flooded with hundreds of posts from students attempting to sell and buy textbooks. Very few students are successful in filtering through these posts to find the right book and price. This project will improve the process and efficiency of buying and selling textbooks among students. Students will be able to search books available by school, major, course, professor, and book condition on the application and/or website. We will have each new member create a login. Students will pay a minimal fee to become a member of the website for six months (a semester). The student will be able to pay this fee with a debit or credit card.
Customer | Tony Messina
Project Core Team: | Bridgette Weirch Karan Patel Piya Mewa Troy Gillispie Dave Gubitosa
Next Milestone: | Example of case scenarios for both mobile app and website.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-01 | Testing | G | 2016-03-31
Design | G | 2016-02-11 | Installation | G | 2016-04-07
Construction | G | 2016-02-11
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
80% of the pages are created in both mobile app and website. We have deteremined to charge a minium fee to actually utilize the app in order to remain profitable. Before the fee, users will be limited to the various functions and be provided with only previews. We have sent out a survey regarding questions on if people have difficulty using FB to buy/sell books and how likely are they to use such an app if developed. 58 responses so far, goal is 100.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Community Site | G | Design |  | 2005-02-01 | 2005-02-03 |  | 2016-02-03 | 2016-02-10
Final project plan | G | Analysis |  | 2016-02-01 | 2016-02-10 |  | 2016-02-10 | 2016-02-10
App/Website Mockup | G | Design
--- User login | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20 | 2016-03-28
--- Account maintenance | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20 | 2016-03-28
--- Catalog maintenance | G | Design |  | 2005-02-01 | 2016-02-17 |  | 2016-03-20 | 2016-03-28
--- Browse catalog | G | Design |  | 2005-02-01 | 2016-02-17 |  | 2016-03-20 | 2016-03-28
--- Add to shopping cart | G | Design |  | 2016-02-01 | 2016-02-17 |  | 2016-03-20 | 2016-03-28
--- Receive contact information | G | Design |  | 2016-02-01 | 17- Feb |  | 2016-03-20 | 2016-03-28
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Challenges |  | G | Figure out how to access all colleges' course IDs and related info |  |  |  | all
Users will be able to do a basic search using Book Title, Author Name, ISBN number. Advanced search will be used to narrow by Course ID, Professor, University, to match books used in similar courses.
Risk |  | G | List out potential risks associated with protoypes in regards to customer data |  |  |  | all
Risk with using apple pay and customer data being somehow exposed. Users can potentially expose themselves and others on their contact information on their own. We will have a team on network and cyber security. Will need users to agree to Terms and Agreement and will post a disclaimer "to not meet anyone that cannot be trusted and we are not responsible for stolen/lost money or what happens during interaction".
Planned Accomplishments
Complete Project Charter, revise all documents, keep working on slide deck, finish last stages of prototypes.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.