## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-01-30
Project Name: | Owl Connect | [5 empty] | Project Status: | G
Project Description: | A Social Media app for Temple University. The app will allow for Temple students to connect with each other based off their profile information. The information that will be needed when you create an account are your Full Name, Graduation Date, Major, Courses Taken/Taking, Temple Organizations involved in, and Temple Activities involved in. When your account is created, you will then be able to find other students by either searching for a student’s name or by searching for the other profile information. When you find a student, you can choose to connect with them. If the student accepts your connection, then that student will become a part of your network. When a student becomes a part of your network, you will be allowed to message them. For example, if you were interested in joining a Temple organization, you can search that organization on the temple app and find people who are in the organization. Then you can connect with students from the organization and message those students to ask questions and get information about that organization.
Customer | Temple Students
Project Core Team: | Christian Wims, Scott Winter, Jason Randolph, Chaimaa Elmalhi, Chuzhuang Jiang
Next Milestone: | Completing the process model, data model, prototype, and system architecture diagram / deck
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-02-06 | Testing | Y | 2018-04-06
Design | Y | 2018-02-13 | Installation | Y | 2018-04-20
Construction | Y | 2018-03-09
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
1.)We started creating our proposal for this project and we are looking forward to presenting it for approval on 1/30/18. 2.) We created the process model, system architecture diagram and deck, and the data model.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Initial planning | G | Plan |  | 2018-01-28 | 2018-01-28 |  | 2018-02-02 | 2018-02-02
Project Charter | G | Analysis |  | 2018-01-29 | 2018-01-29 |  | 2018-01-30 | 2018-01-30
Project Proposal | Y | Analysis |  | 2018-01-30 | 2018-01-30 |  | 2018-01-30 | 2018-01-30
Process Model | G | Plan |  | 2018-02-02 | 2018-02-02 |  | 2018-02-02 | 2018-02-02
System Architecture Diagram and Deck | G | Plan |  | 2018-02-10 | 2018-02-12 |  | 2018-02-12 | 2018-02-12
Data Model | G | Plan |  | 2018-02-15 | 2018-02-15 |  | 2018-02-15 | 2018-02-15
Prototype design | G | Design |  | 2018-02-20 | 2018-02-27 |  | 2018-02-27 | 2018-02-27
--- User login | G | Design |  | 2018-02-20 | 2018-02-20 |  | 2018-02-20 | 2018-02-20
--- N/A | G | Design |  | 2018-02-09 | 2018-02-12 |  | 2018-02-12 | 2018-02-12
--- N/A | G | Design |  | 2018-02-09 | 2018-02-12 |  | 2018-02-12 | 2018-02-12
--- N/A | G | Design |  | 2018-02-09 | 2018-02-12 |  | 2018-02-12 | 2018-02-12
Prototype Beta | Y | Design |  | 2016-02-27 |  |  | 2018-02-27 | 2018-02-27
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Figuring out the roles that best fit us |  | G | Meeting as a group to decide on who does what. |  |  |  | Christian
Updating the status update |  | G | Replanning each step as a group |  |  |  | Jason
Planned Accomplishments
Next week we are planning to meet to discuss the best way in approaching this project and how to design the prototype.