## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-01-30
Project Name: | Owl Connect | [5 empty] | Project Status: | G
Project Description: | A Social Media app for Temple University. The app will allow for Temple students to connect with each other based off their profile information. The information that will be needed when you create an account are your Full Name, Graduation Date, Major, Courses Taken/Taking, Temple Organizations involved in, and Temple Activities involved in. When your account is created, you will then be able to find other students by either searching for a student’s name or by searching for the other profile information. When you find a student, you can choose to connect with them. If the student accepts your connection, then that student will become a part of your network. When a student becomes a part of your network, you will be allowed to message them. For example, if you were interested in joining a Temple organization, you can search that organization on the temple app and find people who are in the organization. Then you can connect with students from the organization and message those students to ask questions and get information about that organization.
Customer | Temple Students
Project Core Team: | Christian Wims, Scott Winter, Jason Randolph, Chaimaa Elmalhi, Chuzhuang Jiang
Next Milestone: | We prepared for our 4th status report for the class. The status report, updated data model, updated process model, updated system architecture diagram, and the project site are all included in this status update. (TECHNICAL ARCHITECTURE AND PROTOTYPE)
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-02-06 | Testing | G | 2018-03-19 |  | G | 2018-03-19
Design | G | 2018-02-20 | Installation | Y | N/A
Construction | Y | 2018-02-27
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
1.)We started prepare for our 3rd status report for the class. The report includes our status report, charter, business case (spreadsheet), prototype, and deck. 2.) We created the beta version of our prototype and begin giving it small tests for the purpose of our presentation
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Update Status Report | G | 4th Report |  | 2018-03-26 | 2018-03-26 |  | 2018-03-26 | 2018-03-26
Project Charter | G | Review |  | 2018-03-14 | 2018-03-14 |  | 2018-03-14 | 2018-03-14
Business Case | Y | Finished |  | 2018-03-13 | 2018-03-13 | Revise the cost and revenue sections | 2018-03-13 | 2018-03-19
Process Model | G | Updating & Finishing |  | 2018-03-20 | 2018-03-20 |  | 2018-03-27 | 2018-03-23
System Architecture Diagram and Deck | G | Updating & Finishing |  | 2018-03-20 | 2018-03-20 | Add more details to the diagram | 2018-03-27 | 2018-03-26
Data Model | G | Updating & Finishing |  | 2018-03-20 | 2018-03-20 | Add x, y, and z, to the model | 2018-03-27 | 2018-03-24
Prototype design | G | Design |  | 2018-02-20 | 2018-02-27 |  | 2018-03-20 | 2018-03-19
--- User login | G | Design |  | 2018-03-13 | 2018-02-20 |  | 2018-03-20 | 2018-03-19
--- Connections Page | G | Design |  | 2018-03-13 | 2018-02-12 |  | 2018-03-20 | 2018-03-19
--- Home Page | G | Design |  | 2018-03-16 | 2018-03-19 |  | 2018-03-27 | N/A
--- Profile Page | G | Design |  | 2018-03-16 | 2018-03-19 |  | 2018-03-27 | N/A
Testing Prototype Beta | Y | Design |  | 2018-03-19 | 2018-03-19 |  | 2018-04-02 | N/A
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Figuring out the roles that best fit us |  | G | Finished |  |  |  | Christian
Updating the Technical Architecture and Prototype |  | Y | Fixing bugs with the protoype |  |  |  | Chuzhuang & Chaimaa
Begin the prototype design |  | G | N/A |  |  |  | Chuzhuang & Chaimaa
Process Model Update |  | G |  |  |  |  | Jason & Scott
System Architecture Diagram Update |  | G | Research Issues |  |  |  | Scott
Data Model Update |  | G | Research Issues |  |  |  | Chuzhuang & Christian
Planned Accomplishments
Next week we are planning to present a status report to the class covering Status report, updated data model, process model, system architecture diagram, and project site.