## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-01-30
Project Name: | BranchOut | [5 empty] | Project Status: | G
Project Description: | A Social Media app for Temple University. The app will allow for Temple students to connect with each other based off their profile information. The information that will be needed when you create an account are your Full Name, Graduation Date, Major, Courses Taken/Taking, Temple Organizations involved in, and Temple Activities involved in. When your account is created, you will then be able to find other students by either searching for a student’s name or by searching for the other profile information. When you find a student, you can choose to connect with them. If the student accepts your connection, then that student will become a part of your network. When a student becomes a part of your network, you will be allowed to message them. For example, if you were interested in joining a Temple organization, you can search that organization on the temple app and find people who are in the organization. Then you can connect with students from the organization and message those students to ask questions and get information about that organization.
Customer | Joe Smith, Manager, Customer Relations
Project Core Team: | Christian Wims, Scott Winter, Jason Randolph, Chaimaa Elmalhi, Chuzhuang Jiang
Next Milestone: | Delivery of Testing plan
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2018-02-06 | Testing | G | 2018-02-06
Design | G | 2018-02-06 | Installation | G | 2018-02-06
Construction | Y | 2018-02-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We started creating our proposal for this project and we are looking forward to presenting it for approval on 1/30/18.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2005-02-01 | 2005-02-01 |  | 2005-02-15 | 2005-02-15
Final project plan | Y | Analysis |  | 2005-12-01 | 2005-12-01 | Scope issues | 2005-12-15 | 2005-01-10
UI Mockup | G | Design
--- User login | G | Design |  | 2005-01-15 | 2005-01-20 |  | 2005-01-22 | 2005-01-22
--- Account maintenance | G | Design |  | 2005-01-20 | 2005-01-20 |  | 2005-01-22 | 2005-01-24
--- Catalog maintenance | G | Design |  | 2005-02-01 | 2005-02-01 |  | 2005-02-03 | 2005-02-03
--- Browse catalog | G | Design |  | 2005-02-01 | 2005-02-01 |  | 2005-02-05 | 2005-02-05
--- Add to shopping cart | G | Design |  | 2005-02-04 | 2005-02-04 |  | 2005-02-06 | 2005-02-06
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Access programmer on vacation |  | G | Jason is out until next week but she can catch up when she returns |  |  |  | Jason
Client trying to make changes |  | R | Client owes us updated changes by this Friday |  |  |  | Client
Planned Accomplishments
Next week we are meeting with the client to cover any scope changes they request. We also plan to deliver a draft of the mock-ups for them to review. When that is approved we can begin the UI design.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.