## Sheet1
Risk | Consequence | Action | Threat Level | Frequency or Large Scale | Status
There are two different expectations for deliverables by the corporate advisor and faculty advisor | Project timeline will be affected if it needs to satisfy both advisors. There may be sacrifices that needs to be made which may have an affect on the quality of the project deliverables. | Discuss with advisors to see if a compromise can be made. Additionally, narrowing the scope can help with minimizing the risk of having the project timeline being delayed. | High | Large Scale
There is a risk that the code may not be fully functional | This will delay certain tasks that requires a functional code before it can be started | Spend more time with thoroughly testing the code to ensure it's working properly before moving on to the next task or step. Additionally, spend more time with the planning process to identify what exact functions need to be implemented in the code before writing the actual code. | Medium | Large Scale
Minor Technical Difficulty preventing continuation of project | Prevent continuation of project | Communicate with our team the importance of working hard to complete all tasks and test properly the first time to prevent repeat tasks. | High | Frequent
There is a risk that the software does not work with the hardware provided | Will prevent and delay the completion of the project | Spend more time with documentation to be able to refer to previous attempts at implementing the software and identify what was already attempted and what went wrong which will allow for better use of time. Accept the risk and narrow down the scope if the end goal is not possible. | High | High Severity
Deadlines continue to be pushed back | goals will never be completed on time, jepordizing the completion of the project | We will discuss the importance and urgancy of getting the small goals completed. And the more small goals that can be completed, the higher quality and hand in a better over all product. | Medium | High Severity
Proposal gets denied | schedule will need to get totally re-worked | We will hold a meeting to discuss possible routes we can take to proposal resubmission | Medium | High Severity
Staying on task during meetings | could lead to push schedule back | Will re work schedule to fit new time line. | Medium | High Severity
Label encoding and testing problems | could lead to push schedule back | Will re work schedule to fit new time line. | Medium | High Severity
OpenMote firmware driver and flashing issues | Hardware would need to be reworked | Will re work schedule to fit new time line. | Low | High Severity
IPv6 Compression algorithhm Contiki not supporting IPv6 extensions | Compression algorithm would need to be rewritten | Will re work schedule to fit new time line. | Low | High Severity