## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-01-31
Project Name: | Temple Course Scheduling | [5 empty] | Project Status: | G
Project Description: | Temple University students need a convenient application to see what courses are needed to graduate. This application would include their major requirements as well as tools that will help students plan, track, and maintain their schedules and courses.
Customer | Fox School of Business Student base
Project Core Team: | Michael Biffen, Jane Kraus, John Kumpf, Justin Teyssier
Next Milestone: | Creating Process Model, Data Model, System Architecture Diagram
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-01-16 | Testing | G | Pro
Design | G | 2018-02-15 | Final Solution Delivery | G | 2018-04-12
Construction | G | 2018-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
This week we had our first team meeting. We were able to get the scope of our project complete, as well as form our project charter document. We prepared to make our first pitch to the sponsors, hoping to gain their apporval. We decided the roles each individual will have for our team and throughout the course of the project.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create Project Schedule | G | Planning |  | 2018-01-28 |  | aptable to change | 2018-01-28
Complete Charter | G | Documentation |  | 2018-01-17 | 2018-01-17 |  | 2018-03-18 | 2018-03-20
Gather ESFF data | G | Analysis |  | 2018-02-08 |  |  | 2018-02-12
Gather Dars data | G | Analysis |  | 2018-02-08 |  |  | 2018-02-12
Layout Application | G | Design |  | 2018-02-10 |  |  | 2018-02-10
Complete 2nd Status Report | G | Documentation |  | 2018-02-06 |  |  | 2018-02-13 | 2018-02-15
Start Business Case | G | Documentation |  | 2018-01-31 |  |  | 2018-01-31
Layout Budget | G | Documentation |  | 2018-02-04 |  |  | 2018-02-04
Process Model | G | Analysis |  | 2018-01-31 |  |  | 2018-02-15
Systems Architecture Model | G | Analysis |  |  |  |  | 2018-02-15
Data Model | G | Analysis |  |  |  |  | 2018-02-15
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Our team does not have a project advisor currently |  | Y | Our project advisor should be assigned within the next few days to help with our project |  |  |  | Jane
We need to create a project budget |  | Y | As we gather our resources we will have a better idea of the total costs of this project |  |  |  | John
We need to gather sufficient data to make our project successful |  |  | Each team member will work together to gather the neccesary information |  |  |  | Justin
Planned Accomplishments
Next week we are meeting with several Fox students to gauge interest in the application as well as improvements to the current system they would like to see. We also hope to meet with a subject matter expert from the Dean's office to gain access to relevant data such as eSFF & DARS.
Note on B47: Key Issues are issues that need your CM Director-level understanding and awareness.