## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-02-14
Project Name: | Temple Course Scheduling | [5 empty] | Project Status: | G
Project Description: | Temple University students need a convenient application to see what courses are needed to graduate. This application would include their major requirements as well as tools that will help students plan, track, and maintain their schedules and courses.
Customer | Fox School of Business Student base
Project Core Team: | Michael Biffen, Jane Kraus, John Kumpf, Justin Teyssier
Next Milestone: | Revised Charter, Business Case, Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-01-16 | Testing | G | Pro
Design | G | 2018-02-15 | Final Solution Delivery | G | 2018-04-12
Construction | G | 2018-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
This week we had our we had multiple meetings to work on our process model, data model and systems architecture diagram. Also two weeks ago we were able to present to the class and hear feedback about our project. This helped us narrow the scope and effectively create our diagrams
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create Project Schedule | G | Planning |  | 2018-01-28 |  | aptable to change | 2018-01-28
Complete Charter | G | Documentation |  | 2018-01-17 | 2018-01-17 |  | 2018-03-18 | 2018-03-20
Gather ESFF data | Y | Analysis |  | 2018-02-08 |  |  | 2018-02-12
Gather Dars data | Y | Analysis |  | 2018-02-08 |  |  | 2018-02-12
Layout Application | G | Design |  | 2018-02-10 |  |  | 2018-02-10
Complete 2nd Status Report | G | Documentation |  | 2018-02-06 |  |  | 2018-02-13 | 2018-02-15
Start Business Case | G | Documentation |  | 2018-01-31 |  |  | 2018-01-31
Layout Budget | G | Documentation |  | 2018-02-04 |  |  | 2018-02-04
Process Model | G | Analysis |  | 2018-01-31 |  |  | 2018-02-15
Systems Architecture Model | G | Analysis |  |  |  |  | 2018-02-15
Data Model | G | Analysis |  |  |  |  | 2018-02-15
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Our team does not have a project advisor currently |  | Y | Our project advisor should be assigned within the next few days to help with our project |  |  |  | Jane
We need to create a project budget |  | Y | As we gather our resources we will have a better idea of the total costs of this project |  |  |  | John
We need to gather sufficient data to make our project successful |  | Y | Each team member will work together to gather the neccesary information |  |  |  | Justin
We need to start creating a business case |  | Y | We are working to understand the possibilites our project could create |  |  |  | Mike
Planned Accomplishments
Since we have process model, data model, and systems architecture diagram we can begin to create our prototype. We have began to start the design layout and our on track with our design schedule. Data collection has become a main priority so after next week hopefully we can go from yellow to green status.
Note on B47: Key Issues are issues that need your CM Director-level understanding and awareness.