## Status Summary
Project Dashboard
[7 empty] | Date: | 2018-03-28
Project Name: | Course Catcher | [5 empty] | Project Status: | G
Project Description: | Universities across the country need a way fro students to easily schedule courses. This system needs to be efficient for both the administration and students. Temple University students specifically need a convenient application to see what courses are needed to graduate. This application would include their major requirements as well as tools that will help students plan, track, and maintain their schedules and courses.
Customer | Fox School of Business Student base and eventually universities across the country
Project Core Team: | Michael Biffen, Jane Kraus, John Kumpf, Justin Teyssier
Next Milestone: | Business Case and Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-01-16 | Testing | G | Pro
Design | G | 2018-02-15 | Final Solution Delivery | G | 2018-04-12
Construction | G | 2018-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Our team has revised all final deliverables. This includes the project charter, process model, systems architecture, data model, and revised the final prototype. We have reached the point where we are creating our final presentation. We are finalizing our business case to show the value of our project. We have a scheduled meeting with our faculty advisor next week and our giving a status update to stakeholers about our project.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create Project Schedule | G | Planning |  | 2018-01-28 |  | Aptable to change | 2018-01-28
Complete Charter | G | Documentation |  | 2018-01-17 | 2018-01-17 |  | 2018-03-18 | 2018-03-20
Gather ESFF data | G | Analysis |  | 2018-02-08 |  |  | 2018-02-12
Gather Dars data | Y | Analysis |  | 2018-02-08 |  |  | 2018-02-12
Layout Application | G | Design |  | 2018-02-10 |  |  | 2018-02-10
Complete 2nd Status Report | G | Documentation |  | 2018-02-06 |  |  | 2018-02-13 | 2018-02-15
Start Business Case | G | Documentation |  | 2018-01-31 |  |  | 2018-01-31
Layout Budget | G | Documentation |  | 2018-02-04 |  |  | 2018-02-04
Process Model | G | Analysis |  | 2018-01-31 |  |  | 2018-02-15
Systems Architecture Model | G | Analysis |  |  |  |  | 2018-02-15
Data Model | G | Analysis |  |  |  |  | 2018-02-15
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Our team does not have a project advisor currently |  | G | We have been assigned and met with our faculty advisor |  |  |  | Jane
We need to create a project budget |  | G | We have created a project budget that is aptable to change |  |  |  | John
We need to gather sufficient data to make our project successful |  | Y | Each team member will work together to gather the neccesary information |  |  |  | Justin
Planned Accomplishments
We need to finalize the prototype. We need to add neccesary functionality to make the process flow better for users. We need to meet with faculty advisors to understand how to store data. Data storage is essential to our project and we need to make storage efficient.
Note on B47: Key Issues are issues that need your CM Director-level understanding and awareness.