## Status Summary
Project Dashboard
[7 empty] | Date: | 2018-03-28
Project Name: | Course Catcher | [5 empty] | Project Status: | G
Project Description: | Universities across the country need a way fro students to easily schedule courses. This system needs to be efficient for both the administration and students. Temple University students specifically need a convenient application to see what courses are needed to graduate. This application would include their major requirements as well as tools that will help students plan, track, and maintain their schedules and courses.
Customer | Fox School of Business Student base and eventually universities across the country
Project Core Team: | Michael Biffen, Jane Kraus, John Kumpf, Justin Teyssier
Next Milestone: | Business Case and Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-01-16 | Testing | G | Pro
Design | G | 2018-02-15 | Final Solution Delivery | G | 2018-04-12
Construction | G | 2018-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Our team has continued to revise all final project documents. We have revised our data model and systems architecture making it more detailed. The charter, business cae, and project website are revised and set up. Oour application developers have added increased funtionality to the prtotype. We are awaiting project feedback from our mentor and classmates.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create Project Schedule | G | Planning |  | 2018-01-28 |  | Aptable to change | 2018-01-28
Complete Charter | G | Documentation |  | 2018-01-17 | 2018-01-17 |  | 2018-03-18 | 2018-03-20
Gather ESFF data | G | Analysis |  | 2018-02-08 |  |  | 2018-02-12
Gather Dars data | Y | Analysis |  | 2018-02-08 |  |  | 2018-02-12
Layout Application | G | Design |  | 2018-02-10 |  |  | 2018-02-10
Complete 2nd Status Report | G | Documentation |  | 2018-02-06 |  |  | 2018-02-13 | 2018-02-15
Start Business Case | G | Documentation |  | 2018-01-31 |  |  | 2018-01-31
Layout Budget | G | Documentation |  | 2018-02-04 |  |  | 2018-02-04
Process Model | G | Analysis |  | 2018-01-31 |  |  | 2018-02-15
Systems Architecture Model | G | Analysis |  |  |  |  | 2018-02-15
Data Model | G | Analysis |  |  |  |  | 2018-02-15
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Our team does not have a project advisor currently |  | G | We have been assigned and met with our faculty advisor |  |  |  | Jane
We need to create a project budget |  | G | We have created a project budget that is aptable to change |  |  |  | John
We need to gather sufficient data to make our project successful |  | Y | Each team member will work together to gather the neccesary information |  |  |  | Justin
Planned Accomplishments
After review from the class and mentors we will revise and add to the prototype. All other documents need to be reviewed but are completed. After that we can finalize of final presentation and prepare for the presentation itself.
Note on B47: Key Issues are issues that need your CM Director-level understanding and awareness.