## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date:
Project Name: | Course Search (Working Title) | [5 empty] | Project Status: | Y
Project Description: | Temple University’s course search currently requires students to search by department or GenEd area goal followed by sifting through course sections. It is inefficient and difficult for students to find courses they are interested in taking. The GenED department expects a banner update and they desire better search functionality in the update. The purpose of this project is to determine a solution which will require no recurring costs while allowing the GenED department to add an improved search function. The function should allow students to search for any class based on keywords/categories that pertain to class topics or sub-topics and decrease the amount of time it takes to find/add a course.
Customer | Temple University General Education Department
Project Core Team: | Quy Le, Kevin Diem, Darpan Patel, Michael Black
Next Milestone: | Accurate clusters/categories
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | MM/DD/YY | Testing | R | MM/DD/YY
Design | G | MM/DD/YY | Installation | R | MM/DD/YY
Construction | R | MM/DD/YY
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | R
Major Accomplishments/Decisions
Completed foundational work for text anaysis with two different tools. Completed beta version of course search + result pages, ready for initial feedback.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Recieve feedback on initial design | G
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Collecting syllabi |  | Y | Meeting planned with TUPortal team 2/3/17 |  |  |  | Kevin
Planned Accomplishments
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.