## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-03-08
Project Name: | Course Search (Working Title) | [5 empty] | Project Status: | Y
Project Description: | Temple University’s course search currently requires students to search by department or GenEd area goal followed by sifting through course sections. It is inefficient and difficult for students to find courses they are interested in taking. The GenED department expects a banner update and they desire better search functionality in the update. The purpose of this project is to determine a solution which will require no recurring costs while allowing the GenED department to add an improved search function. The function should allow students to search for any class based on keywords/categories that pertain to class topics or sub-topics and decrease the amount of time it takes to find/add a course.
Customer | Temple University General Education Department
Project Core Team: | Quy Le, Kevin Diem, Darpan Patel, Michael Black
Next Milestone: | Update Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2017-02-15 | Testing | R | 2017-03-23
Design | Y | 2017-03-07 | Installation | R | 2017-04-15
Construction | Y | 2017-03-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | R
Major Accomplishments/Decisions
Created basic template for page. Received authorization & funding for holding a focus group. Conducted focus group, and gained insight into flaws and benefits of prototype. Enhanced template for page, and added
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Meet with Project Sponsor to plan focus group | G |  | Planning | 2017-03-08
Focus Group | G | Planning |  | 2017-03-22 |  |  | 2017-03-22
Refine interface in time for focus group | G |  |  | 2017-03-08 |  |  | 2017-03-20
Meet with Mentor | G |  |  | 2017-03-22 |  |  | 2017-03-22
Second meeting with Mentor | G |  |  | 2017-03-25 |  |  | 2017-03-27
Project Powerpoint | Y |  |  | 2017-03-26 |  |  | 2017-04-19
Enhance Prototype | Y |  |  | 2017-03-24 |  |  | 2017-04-19
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Getting a focus group data |  | Y |  |  |  |  | Quy
Planned Accomplishments
Meet with sponsor to review focus group questions and refine to the best for discussion. Hold focus group. Get feedback from end-users on the current process. Design new process using feedback.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.