## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-02-15
Project Name: | Dibs | [5 empty] | Project Status: | Y
Project Description: | We are addressing the problem of long wait times for customers to be served at dine-in restaurants. We also want to provide customers the option of ordering their entrees prior to arrival. Our solution will allow restaurants to better manage their customer traffic, utimately enhancing the customers' experience.
Customer | Dine-in restaurants and consumers
Project Core Team: | Malik Donald, Noah Fulkroad,Jose Gil, Parth Patel, Ajah Puryear
Next Milestone: | Creation of Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-02-08 | Testing | Y | 2018-04-12
Design | G | 2018-02-15 | Installation | Y | 2018-04-24
Construction | Y | 2018-03-13
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We received approval for our idea from MIS 4596 classmates.
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Data and Process Model | G | Analysis/Design |  |  | 2018-02-14 |  | TBD | TBD
System Architecture | G | Analysis/Design |  |  | 2018-02-14 |  | TBD | TBD
Project Charter | G | Documentation |  | 2018-01-31 | 2018-01-31 |  | TBD | TBD
Test plan | G | Design |  | 2005-02-01 | TBD |  | 2005-02-15 | TBD
Final project plan | Y | Analysis |  | 2018-04-12 | TBD | Scope issues | 2018-04-12 | TBD
Application Design | Y | Design |  | 2018-02-15 | TBD
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
Begin working on prototype and meet with mentor for the first time.
Note on B42: Key Issues are issues that need your CM Director-level understanding and awareness.