## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-02-15
Project Name: | Dibs | [5 empty] | Project Status: | Y
Project Description: | We are addressing the problem of long wait times for customers to be served at dine-in restaurants. We also want to provide customers the option of ordering their entrees prior to arrival. Our solution will allow restaurants to better manage their customer traffic, utimately enhancing the customers' experience.
Customer | Dine-in restaurants and consumers
Project Core Team: | Malik Donald, Noah Fulkroad,Jose Gil, Parth Patel, Ajah Puryear
Next Milestone: | Creation of Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-02-08 | Testing | Y | 2018-04-12
Design | G | 2018-02-15 | Installation | Y | 2018-04-24
Construction | Y | 2018-03-13
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We have storyboarded our prototype outside of justinmind. This week we plan to begin prototyping our project. We have a meeting with our mentor to introduce ourselves, go over the project and receive any form of feedback and/or knowledge.
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Data and Process Model | G | Analysis/Design |  |  | 2018-02-14 |  | TBD | TBD
System Architecture | G | Analysis/Design |  |  | 2018-02-14 |  | TBD | TBD
Project Charter | G | Documentation |  | 2018-01-31 | 2018-01-31 |  | TBD | TBD
Test plan | G | Design |  | 2005-02-01 | TBD |  | 2005-02-15 | TBD
Final project plan | Y | Analysis |  | 2018-04-12 | TBD | Scope issues | 2018-04-12 | TBD
Project Team Site | R | Final |  | 2018-03-27 |  |  | 2018-04-10
Application Design | Y | Design |  | 2018-02-15 | TBD
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Mentor Meetings |  | G | We have find time to meet with our mentor that works for everyone. |  |  |  | Ajah
Planned Accomplishments
Next week we are aiming to complete the protoype and begin working on the project team site. We will also be updating our deliverables such as the project charter.
Note on B43: Key Issues are issues that need your CM Director-level understanding and awareness.