## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-09-17
Project Name: | Managing Your Digital Identity | [5 empty] | Project Status: | G
Project Description: | We will design an application that will connect with Google, Facebook and other social media API's to retrieve photos of our users. Those photos will be used to cross-check them on different platforms that the user's photos show up in. When that happens, the user will be notified that their photo is being used in a different platform and if it is an unauthroized use, we will use a third party to take that photo down to prevent 'catfishing' and reputation damage
Customer | College Students, University Career Centers
Project Core Team: | Mia Jardine, Noah Mercado, Kimberly Eastlake, Ryan Pace, Nodir Zakhidov
Next Milestone: | Analysis
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-15 | Testing | Y | 2016-10-20
Design | Y | 2016-09-16 | Installation | Y | 2016-11-15
Construction | Y | 2016-09-22
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
This week we met as an entire unit, delegated a few tasks, and decided on the direction we want to go. We will continue to research this idea and any implications/limitations. Furthermore, we will futher develop the business case of this idea to ensure that there is value to this application.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | Y | Research & Design |  | 2016-09-15 | 2016-09-17 | Still in development | 2016-09-29
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Research needs to be done for strategy and Business Rule |  | Y | N/A |  |  |  | Group
Business Case is Weak |  | Y |  |  |  |  | Ryan Pace & Group
Planned Accomplishments
Next week we plan on revising the project charter to correct and errors and to add more information. Also we plan on meeting up again to discuss project updates and further develop our idea, goals, risks and actionables plans
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.