## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-09-29
Project Name: | Managing Your Digital Identity | [5 empty] | Project Status: | Y
Project Description: | We will design an application that will connect with Google, Facebook LinkedIn, Instragram, and other social media API's to retrieve photos of our users. Those photos will be used to cross-check them on different platforms that the user's photos show up in. When that happens, the user will be notified that their photo is being used in a different platform and if it is an unauthroized use, we will use a third party to take that photo down to prevent 'catfishing' and reputation damage. The user will also receive a social media "score" based on others within their network where they can see how they measure up based on professionalism, reliability, and skillsets to get a job in the future.
Customer | College Students, University Career Centers, Company Recruiters
Project Core Team: | Mia Jardine, Noah Mercado, Kim Eastlake, Ryan Pace, and Nodir Zakhidov
Next Milestone: | Design
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-29 | Testing | Y | 2016-10-20
Design | Y | 2016-09-30 | Installation | Y | 2016-11-15
Construction | Y | 2016-10-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
We decided to change the scope and business case of the project because there was a limited need for a subscription-based product. We also changed the target audience for this product and move away from online identity theft and instead create an online "score" so users can measure their social media presence to get a job and remain professional online. This week we met as a group to revise the project charter and delegate tasks so each member of the group can "own" parts of the project. Kim and Ryan are documentation leads; Noah, Mia, and Nodir are technology design and prototype leads. We will continue to research this idea and map out a design for the prototype. There may be limitations for what JustInMind can do, so those will be recognized and recorded by the end of this week. Furthermore, we will futher develop the business case of this idea to ensure that there is value to this application.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | Y | Research & Scope |  | 2016-09-29 | 2016-09-30 | Final changes need to be made | 2016-10-01 | Need to make sure there is no scope creep
Prototype Design Plan | Y | Design |  | 2016-09-30 | 2016-10-06 | JustInMind map | 2016-10-10
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Research needs to be done for strategy and Business Rules |  | Y |  |  |  |  | Group
Business Case is Weak |  | Y |  |  |  |  | Group
Scope needs to be changed |  | R
Planned Accomplishments
Our Project Charter is finalized this week, so we can begin created a plan for the design of our prototype. We want to ensure that what we have decided to create is possible within the time-frame and budget constraints. Also we plan on meeting up again to discuss project updates and further develop our idea, goals, risks and actionables plans
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.