## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-10-03
Project Name: | Managing Your Digital Identity | [5 empty] | Project Status: | Y
Project Description: | We will design an application that will connect with Google, Facebook LinkedIn, Instragram, and other social media API's to retrieve photos of our users. Those photos will be cross-check and given a percentage of harmful content. (i.e. percent "party" or "alchohol") The percentage will allow users to find images that would damage their reputation. In addition, users can increase their professional reputation using scores for content such as emails, cover letters, online posts, and resumes uploaded/ran through the application. The user will also receive a social media "score" based on others within their network where they can see how they measure up based on professionalism, reliability, and skillsets to get a job in the future.
Customer | College Students, University Career Centers, Company Recruiters
Project Core Team: | Mia Jardine, Noah Mercado, Kim Eastlake, Ryan Pace, and Nodir Zakhidov
Next Milestone: | Design
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-29 | Testing | Y | 2016-10-20
Design | Y | 2016-09-30 | Installation | Y | 2016-11-15
Construction | Y | 2016-10-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
We were able to formulate a business case for our solution and we will focuse on targeting universities and individual students in the beginning phase of our offerings. As our customer base grows, we will target job seach sites such as Monster as one of their offerings to their members. This is what we are leaning towards but that can change with new information in the future. We also were able to find APIs provided by IBM Watson that allows us to have image recognition capabilities that will enhance our final solution.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Research & Scope |  | 2016-09-30 | 2016-10-13 | Final changes need to be made | 2015-10-11 | Need to make sure there is no scope creep
Prototype Design Plan | R | Design |  | 2016-09-30 | 2016-10-13 | Design & Architeture | 2016-10-10 | Create foundation for actual application
Use Case | Y | Design |  | 2016-10-03
Financials | Y | Metrics/Cost Analysis |  | 2016-10-13 | 2016-10-18 | Define area of costs/profits | 2016-10-13 | Create monetization for application
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Design systems architecture |  | Y |  |  |  |  | Group
Business Case is Weak |  | Y | Find an actual case and develop personas |  |  |  | Group
Financial Metrics |  | Y | Monetize application. Use business rule/requirements to find associated costs |  |  |  | Group
Planned Accomplishments
Our project has a finalized concept and design. We need to map the architecture of the application and organizations using it. We are planning on making a work flow in order to understand the architecture and understand our customers and actors. The basic design is developed, now we have to develop further to a finalized deliverable.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.