## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-10-27
Project Name: | Managing Your Digital Identity | [5 empty] | Project Status: | Y
Project Description: | We will design an application that will connect with Google, Facebook LinkedIn, Instragram, and other social media API's to retrieve photos of our users. Those photos will be cross-check and given a percentage of harmful content. (i.e. percent "party" or "alchohol") The percentage will allow users to find images that would damage their reputation. In addition, users can increase their professional reputation using scores for content such as emails, cover letters, online posts, and resumes uploaded/ran through the application. The user will also receive a social media "score" based on others within their network where they can see how they measure up based on professionalism, reliability, and skillsets to get a job in the future.
Customer | College Students, University Career Centers, Company Recruiters
Project Core Team: | Mia Jardine, Noah Mercado, Kim Eastlake, Ryan Pace, and Nodir Zakhidov
Next Milestone: | Testing
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-29 | Testing | R | 2016-11-15
Design | Y | 2016-09-30 | Installation | R | 2016-12-01
Construction | R | 2016-10-27 | Financials | Y | 2016-11-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | R | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
We have isolated two key features of the application for testing.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Research & Scope |  | 2016-09-30 | 2016-10-13 | Final changes need to be made | 2015-10-11 | Need to make sure there is no scope creep
Prototype Design & Architecture | R | Design |  | 2016-10-03 | 2016-10-27 | Front End & Back end development | 2016-10-10 | Continous development for testing
Use Case | Y | Implementation and Design |  | 2016-10-10 | 2016-10-27 | Test usage against use case |  | Compare use case to functionality
Financials | Y | Metrics/Profit Analysis |  | 2016-10-13 | 2016-10-18 | Define profit structure | 2016-10-27 | Create monetization for application
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Design systems architecture |  | R | Developing front end and backend framing. Move to next phase of completion by 11/1/2016 |  |  |  | Noah & Ryan
Final Documentation |  | Y | Gather final deliverable criteria and completed documents |  |  |  | Kim
Financial Metrics--Profit |  | Y | Monetize application. Use businesscase to create strategy for monetization |  |  |  | Mia
Planned Accomplishments
Our project has a finalized business case, and a business plan. We will have a preliminary protoype designed, with limited functionality by next class meeting. The only limitation is functionality, we will focus on a few features of the application in order to move into testing against the use case and finalizing design.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.