## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-11-15
Project Name: | Managing Your Digital Identity (My.di) | [5 empty] | Project Status: | Y
Project Description: | We will design an application that will connect with Google, Facebook LinkedIn, Instragram, and other social media API's to retrieve photos of our users. Those photos will be cross-checked based on inappropriate content (i.e. percent "party" or "alcohol"). The percentage will allow users to find images that would damage their reputation. In addition, users can increase their professional reputation using tone and visual recognition features such as analyzing content on emails, cover letters, online posts, and resumes uploaded/ran through the application. The user will also receive a social media "score" based on others within their network where they can see how they measure up based on professionalism, reliability, and skillsets to get a job in the future.
Customer | University Career Centers, Company Recruiters
Project Core Team: | Mia Jardine, Noah Mercado, Kim Eastlake, Ryan Pace, and Nodir Zakhidov
Next Milestone: | Testing
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-29 | Testing | Y | 2016-11-15 | Planning | G | 2016-08-29
Design | R | 2016-10-01 | Installation | Y | 2016-12-01
Construction | R | 2016-10-27 | Financials | Y | 2016-11-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | R | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
The Project Charter is in its fifth revision and has undergone intense revisions based on feedback from our professor. We have made major headway in terms of financial analysis and building a realistic business case. Communication and collaboration amongst the team has greatly improved. The application development is also in a good place. We have to make some decisions about how to pull it all together, but overall our solution has come a long way since the last status report.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Research & Scope |  | 2016-09-30 | 2016-11-10 | Final revisions need to be made | 2016-11-17 | Need to make sure there is no scope creep and get feedback from project mentor
Prototype Design & Architecture | R | Design |  | 2016-09-18 | 2016-11-14 | Front-end & back-end development | 2016-11-15 | Need to draft high-level enterprise architecture design
Use Case | R | Implementation and Design |  | 2016-10-10 | 2016-10-27 | Test application functionality | 2016-11-15 | Compare prototype design and functionality against use cases
Financials | Y | Metrics/Profit Analysis |  | 2016-10-13 | 2016-10-18 | Project net benefit over 5 years | 2016-10-27 | Monetize metrics in terms of projected financial benefit
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Design systems architecture |  | R | Developing front end and backend framing. Move to next phase of completion by 11/15/2016 |  |  |  | Noah & Ryan
Final Documentation |  | Y | Gather final deliverable criteria and completed documents |  |  |  | Kim
Financial Metrics--Profit |  | Y | Monetize application and metrics. Use business case to create strategy for monetization |  |  |  | Mia
Website |  | Y | Ensure the website is polished and informative to market our solution |  |  |  | Kim & Nodir
Planned Accomplishments
Our project has an almost finalized business case, and a business plan. The next step is to tighten the metrics in the Project Charter. We need to quantify our metrics and the benefits our target customer, colleges and universities, will take from this. For example, we need to quanitfy how much 3-5% higher job placement is worth to the Fox School of Business. We will have an almost final protoype designed, with functionality by next class meeting. Our biggest threat is timing, which we are mitigating through many group meetings and consistent communication. We hope to also have
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.