## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-02-11
Project Name: | MedNerx | [5 empty] | Project Status: | Y
Project Description: | Taking an inside look at the medical industry our team has identified inconsistencies and troubled areas. Our objective is to focus on customer relationship management for the patient at the same time improving operational flow in the medical space.
Customer | Hosptials, Medical Facilities and our end user/client will be the Patient.
Project Core Team: | Jeremy John, Alan Kim, Johnathan Holland, George J Raymond
Next Milestone: | Data Modeling, Process Model and System Architecture
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Initial | Y | 2017-02-12 | Testing | R | 2004-05-15
Planning | G | 2017-02-16 | Installation | R | 2017-03-07
Execution | R | 2017-02-14
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
This week our team focused our efforts on the Project Charter to assure that our abjectives will help us mover towards decreasing Healthcare Spending. We are aiming to decrease Healthcare spending by focusing on Patient Engagement. We have created our Workbreakdown structure to provide a schedule of who, what, when and how tast will be completed. With new regulations for hospitals to provide accurate, up to date and reliable information amount patients, treatment and diagnoses our application will provide a solution in all these areas.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Initial |  | 2017-02-10 | 2017-02-12 |  | 2017-02-12 | 2017-02-12
WBS | G | Planning |  | 2017-02-08 | 2017-02-11 | Trouble Objectives/Project | 2017-02-13 | 2017-02-11
Prototype | G | Execution
SwimLane | R | Planning |  | 2017-02-13 | 2017-02-13 | slow start Projece Chart | 2017-02-13 | -
--- Data Modeling | R | Planning |  | 2017-02-13 | 2017-02-13 |  | 2017-02-13 | -
--- Systems Architecture | R | Planning |  | 2017-02-13 | 2017-02-13 |  | 2017-02-13 | -
--- Design Prototype | R | Planning |  | 2017-02-14 | 2017-02-21 |  | 2017-02-21 | -
--- Functionality | R | Planning |  | 2017-02-14 | - |  | 2017-02-20 | -
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Indentifying Our core Solution |  | G | Our team has indentified our project objectings. |  |  |  | Jeremy/George
Identifing a real problem in Medical space |  | G | Our team faced challenges identifing a value propositon |  |  |  | Jeremy/George
project Charter |  | G | This is key to assure that our team is solving a problem that is real |  |  |  | Team Effort
Planned Accomplishments
Next week our goal is to have a solution documented that will offer all our team members a visual understanding of how the aplication will work. In addition we are going to complete our Swim Lane Diagram to help our developers move in the right direction while creating the prototype.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.