## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date:
Project Name: | DocuMed | [5 empty] | Project Status: | R
Project Description: | Taking an inside look at the medical industry our team has identified inconsistencies and troubled areas. Our objective is to focus on customer relationship management for the patient at the same time improving operational flow in the medical space.
Customer | Hospitals, Medical Facilities and our end user of client will be Patient
Project Core Team: | Jeremy John, Alan Kim, Johnathan Holland, George J Raymond
Next Milestone: | Data Modeling, Process Model and System Architecture
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2017-02-12 | Testing | Y | 2017-03-08
Design | R | 2017-02-16 | Installation | Y | 2017-03-08
Construction | R | 2017-02-14
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | R | On-Budget |  | Y | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Our team have identified the project focuss. We noticed that it is easy to get off topic to solve problems outside of our scope. It is very important for our project manager to stay on course. Our project is focused on the medical industry in an area that has many variables. Our work breakdown structure is very important to help us keep on course. Our team is collaborating weekly. We identified roles for our partners to establish structure and gain control of where our project is moving.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | Y | Design |  | 2005-02-10 | 2005-02-12 | Not 100%,need work | 2/12//2017 | 2017-02-23
WBS | Y | Analysis |  | 2017-02-08 | 2017-02-11 | Still need clarify | 2017-02-11
SwimLane | R | Design |  | 2017-02-16 |  | Not on course | 2/16/2-17
--- Prototype Design | R | Design |  | 2017-02-14 |  | Not on course | 2017-02-20
--- Layout | R | Design |  | 2017-02-23 |  | not on course, | 2017-02-23
--- System Architecure | R | Design |  | 2005-02-13 |  | Team not on course
--Functionality | R | Design |  | 2014-02-21 |  | not on course | 2017-02-26
--- Business Rules | R | Design |  | 2017-02-17 |  | Not on course
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Team doesn’t seem to have clear idea solution |  | Y | Our team has not clarified and exact solution. We have general idea. |  |  |  | team
What will our prototype look like. |  | R | Client owes us updated changes by this Friday |  |  |  | team
Are we creating the back end solution? |  | R | We are unclear as to what amount of the back end we must create? |  |  |  | team
Planned Accomplishments
we created our WBS. We have also clarified the project charter to give our team a better understanding of the direction we are going. With this we have not yet clarified what the solution will look like. This week will be very important for our team to meet and clarify how the project will function, the layout and the design. We also will clarifiy how much of the back end work is required and what our deliverables are.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.