MIS 4596 TEAM 4

Project Charter

| Project Title | DreamBIG | Product/Process Impacted | College Application Process |
| --- | --- | --- | --- |
| Start Date | 2/7/2014 | Organization/Department | Temple University MIS Department |
| Target Completion Date | 4/30/2014 | Champion | TBA |

|  |  | ## Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Project Description |  | What problem is the team addressing? What problems do customers have? High school students need to be more well-informed of the college admissions process and receive personal attention as soon as they start 9th grade. Students do not know what it takes to get into their dream school until it is too late. Guidance counselors are typically responsible for seeing 200 to 300 students per. Students do not receive enough personal attention about the college prep process. Also, finding low-cost tutors is another problem. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Project Scope |  | What areas are inside and/or outside the work of the team? What are the boundaries (start and end points)? What specific parts of the overall problem will you focus on? Boundaries- HS students (grades 9-12th) We are focusing on giving the students more personalized attention and provide them with the advice and tools they need to get into their dream school. We are linking academic performance to realistic college choices. We are going to create an application that tracks and monitors student’s grades and extracurricular activities. The website will then show the student what school they are on pace to get into and how they measure up against getting into their dream school. The student will receive personalized feedback on what they need to improve on for example if the student lacks volunteer activities, we would recommend volunteer events going on in their area. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Project Goal and Deliverables What must the team deliver to be successful? Does the team goal link to the key performance parameters established by the sector leadership teams? What is the baseline performance? How will the goal be measured? Business requirements, website, and connection with tutors |  |  |  |  |  |  |  | Metrics (propose specific metrics for your project, e.g., cost reduction, time reduction, customer satisfaction, etc.) |  | Baseline | Current |  | Goal |  |  |  |  |
| Users must believe that our product is effective in order for our company to become profitable. Users may questions the concept of on-line counseling. |  |  |  |  |  |  |  | User Acceptance |  | 1,000 | 0 |  | Reach 1,000 active users in year 1 |  |  |  |  |
| Our sales growth must continue to increase in order to attract investors and continue to grow the compnay and pay for our overhead. |  |  |  |  |  |  |  | Sales Growth |  | $500,000 | 0 |  | Reach $500,000 in sales in two years |  |  |  |  |
| Users must achieve results by using our product. If this does not improve student academic performance or streamline the college application process we will not be successful. |  |  |  |  |  |  |  | Grades Improvement |  | 20 % | 0 |  | Increase student grades by one letter grade |  |  |  |  |
| Our users must be active. They must continue to use our product inorder to achieve an increase in active user growth over a few year time period. |  |  |  |  |  |  |  | Active User Growth |  | 1,000 | 0 |  | Increase by 40% annually |  |  |  |  |
| 4. Business Results Expected |  |  |  | Create a website that tracks and monitors students grades so they can receive personalized feedback and tools on how to improve their chances of getting in to their dream college. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Team members |  |  |  | Who is this team accountable to? Who is your champion? Who is on this team? What are the specific skills/roles of each team member? Who can the team turn to for expert guidance? The team is accountable to Professor Hohne Team consists of: Joe Nespoli- Financials, Design, Business Model, Idea champion Jason Lee- Design, JustinMind Dave Dupell- Financials, Design, Revenue streams Patrick Cantelmi- JustinMind, Design, Marketing Kayla Shaffer- JustinMind, Database Management, Marketing Expert guidance- Our mentor and the MIS department |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Support Required and risks |  |  |  | What additional resources does the team need? What obstacles does the team see, and how can they be resolved? Low-cost tutors for the HS students, Site administrator, Developer, Domain and Hosting costs, Access to college rankings, lawyer and patent fees Obstacles- Students not inputting accurate grades, creating a database of schools Resolved-Students must upload a picture of their report card (or student/parent gets discount if they upload report card), get school rankings from a 3rd party site like US news |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Customer Benefits |  |  |  | How will this project help the customer of the organization? Could improvements have a negative impact on the customer? The website would streamline the college application process and provide guidance to young applicants. This site would encourage early college planning and send reminders of application deadlines to students and parents. The site will consider student academic performance and other criteria and provide the best college options to the student. Currently, the market does not offer a site that links academic performance and the college selection process. Also, our competitors fail to provide accurate information about college rankings and what corporations recruit from specific schools. We are college students that have been in the shoes of our customers and our site will capture the whole picture of the college selection process. Our site will could not negatively impact the customer. Our site will keep our customers well informed so they can choose the best school to attend. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Technology Architecture |  |  |  | What are the specific tools/technologies you will be using? What is the experience of team members with these tools? JustinMind prototyper Lean Canvas Website creation Wordpress |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Overall schedule/Work Breakdown Structure (Key milestones & dates) |  |  |  |  |  | Responsible individual |  |  | Output (notes, diagrams, interviews, screen prints) |  |  | Date started if in progress Or Expected completion date |  | Date completed or date completion is expected |  |  |  |
| Planning |  |  |  |  |  | Joe Nespoli |  |  | Interviews |  |  | In Progress 2/10 |  | Not Completed 2/23 |  |  |  |
| Analysis |  |  |  |  |  | Dave Dupell |  |  | Research |  |  | In Progress 2/10 |  | Not Completed 2/23 |  |  |  |
| Design |  |  |  |  |  | Dave Dupell Joe Nespoli |  |  | Diagrams |  |  | Not Started 2/23 |  | Not Completed 3/2 |  |  |  |
| Implementation: Construction |  |  |  |  |  | Jason Lee Patrick Cantelmi Kayla Schaffer |  |  | Prototype |  |  | Not Started 3/2 |  | Not Completed 3/16 |  |  |  |
| Implementation: Testing |  |  |  |  |  | Jason Lee Patrick Cantelmi Kayla Schaffer |  |  | User Acceptance Testing |  |  | Not Started 3/16 |  | Not Completed 3/23 |  |  |  |
| Installation |  |  |  |  |  | Jason Lee Patrick Cantelmi Kayla Schaffer |  |  | Prototype |  |  | Not Started 3/23 |  | Not Completed 3/30 |  |  |  |

Charter Development Guidelines: Examples are in italics.  You can expand the form to meet your requirements as you enter text.

Project Title: Enter the name for your project – the name should convey a sense of purpose.  Should contain an action word; such as – improve, develop, implement, reduce, etc.

Reduce Cycle Time for Resolving Disability Disputes

Product/Process Impacted: What you are working on.

Disability Claim Process

Champion:  The sponsor of the project.

Department Head

Organization: Where you work.

Corporate HQ – Shared Services

Start Date: This is the first day on the project.

Target Completion Date: This is depending on the negotiated time line and scope with the sponsor.

- Project Description: Several sentences addressing: why you are undertaking this project, the magnitude of the problem, general approach to be taken and expected benefits.

The Shared Services Benefits Group receives on average 30 claim appeals per month.  Many of these are resolved by providing information clarifying the process and others should have been handled locally or by directly working with the service provider.  This project will improve the process currently in use so that calls/claims are resolved quicker.  This will allow members of this organization to focus on more strategic issues and will improve client satisfaction and eliminate re-work.

- Project Scope: What the boundaries are of the process that you are going to be working on.

This "Process" begins with opening of a claim dispute and ends when the disputed claim case being closed.

- Project Goal: Describe the target(s) that you are planning to achieve.  Reduce cycle time by 50%, reduce cost per computer installation by 50% etc.  If you don’t have a quantifiable target then you cannot claim that you have reached your goal.

Include the historical baseline information. The current value for the process will be updated as the project progresses toward your goal.

For cycle time: Baseline- 2 days,  Current- 2 days, Goal- 1 day  (the goal reflects the 50% reduction from baseline)

For cost: Baseline- $1000, Current- $800, Goal- $500 (the goal reflects the 50% reduction from baseline)

You may have other metrics that you are working to impact; if so, substitute them for any that don’t apply.  You may have only one metric and will rarely have more than three.

- Business Results:   What the benefits are to your organization when this project is complete.  How will this project impact your organizations “Dashboard” metrics?  What will be the impact to the financial bottom line?

- Team Members: List the dedicated team members and also any other regular contributors to the success of the project.

- Support Required: Identify other resources that may be required, such as outside consultants etc.

- Customer Benefits: What the benefits are to the customers of this project if the process/product is improved.

The people using the claims dispute process will get faster results and resolution of their claim.  This should result in better customer satisfaction levels with the process as well as improved productivity of service operators through fewer status inquiries.

- Technology Architecture:  What are the tools you will be using (development tools, data base, etc)?  How will you obtain the tools?  What is the level of experience of specific team members with these tools?

- Schedule: Enter the anticipated dates that you will complete each phase of the project; work with your champion to determine these dates.