## Status Summary
Project Dashboard
[7 empty] | Date: | 2015-01-27
Project Name: | FindYourFit | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Smartphone users seeking a certified fitness instructor within the area.
Project Core Team: | Nick Hockley, Dan Matronia, Alexander Savon
Next Milestone: | 1 - Completion of design and research 2 - Application design rough draft
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-03 | Testing | R | 2016-03-30 |  | Y | 2016-01-27
Design | R | 2016-02-24 | Installation | R | 2015-04-13
Construction | R | 2016-03-16
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | Y | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Last week we presented our initial project ideas and recieved constructive feedback from the class and our instructor. Our first choices did not qualify, but after brainstorming with our third teammate for the first time we were able to verify a new project lead, which was deemed acceptable,
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Research & Analysis | Y | Design |  | 2016-01-27 | 2016-01-27 | Underway | 2016-02-03 | 2016-02-03
Project Plan | Y | Design |  | 2016-01-27 | 2016-01-27 | Assignment needed | 2016-02-10 | 2016-02-10
Project Charter | G | Design |  | 2016-01-20 | 2016-01-20 | Rough copy complete | 27- Jan
Role Assignment | Y | Planning |  | 2016-01-27 | 2016-01-27 | complete | 27- jan
G
G
G
G
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
The decision between an app or website |  | Y | We have decided to go with an smartphone application |  |  |  | Team
Creating the design of the product |  | Y | With little JIM experience, we need to figure out how this will function |  |  |  | Team
Planned Accomplishments
We are now in the planning and initial analysis stages, meaning we are resreaching and planning out how we are going to approach the project within the given time frame. Once complete we will start work on the rough draft of our application design.