## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-03-23
Project Name: | FindYourFit | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Smartphone users seeking a efficient and safe workout with a experienced professional in their area
Project Core Team: | Nick Hockley, Dan Matronia, Alexander Savon
Next Milestone: | 1. Finalized Prototype 2. Update Team Site 3. Start Project Deck
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-03 | Testing | R | 2016-03-30 |  | Y | 2016-01-27
Design | G | 2016-02-24 | Installation | R | 2015-04-13
Construction | R | 2016-03-16
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | Y | Delivery to Scope |  | Y
Major Accomplishments/Decisions
These past couple of weeks have been focused on prototype functionality. We have completed a working project site, which will be updated along with the project. The next couple of week will be devoted to the construction and full completion of the prototype. We are constantly researching the fitness industry to ensure that our application is to the standards that the industry expects. We have also conducted interviews with a personal trainer to truelly access the need of an applicaiton such as this in the market.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Research & Analysis | Y | Design |  | 2016-01-27 | 2016-01-27 | Underway | 2016-02-03 | 2016-02-03
Project Plan | G | Design |  | 2016-01-27 | 2016-01-27 | Assignment needed | 2016-02-10 | 2016-02-10
Project Charter | G | Design |  | 2016-01-20 | 2016-01-20 | Rough copy complete | 27- Jan
Role Assignment | G | Planning |  | 2016-01-27 | 2016-01-27 | complete | 27- jan | 2016-02-02
Prototype Building | R | Design |  | 2016-02-02 | 2016-02-22 | Underway | 2016-04-06
Final Presentation | Y | Presentation |  | 2016-04-01 | 2016-04-01 |  | 2016-04-10
Team Webite | Y | Planning |  | 2016-03-22 | 2016-03-22 | Underway
G
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
The decision between an app or website |  | Y | We have decided to go with an smartphone application |  |  |  | Team
Creating the design of the product |  | Y | With little JIM experience, we need to figure out how this will function |  |  |  | Team
Prototype Design |  | R | Our protype is behind schedule as of now; however, we are devoting resources in the coming weeks to remedy the situation. |  |  |  | Team
Planned Accomplishments
We have completed the majority of our research for the project; however, we need to be aware of changes, such as fitness trends as well as certification standards, in the industry and thus plan for that. Our main goal in the coming weeks is the completion/fine tuning of our prototype of the application. We plan on updating our project site as the project continues. Our site is up and running with the key documents we have used in the project; however, the site still needs to be updated with infromation from the project in the coming weeks. We also will begin planning on our final presnentaiton in the coming weeks.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.