## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-03-09
Project Name: | FindYourFit | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Smartphone users seeking a certified fitness instructor within the area.
Project Core Team: | Nick Hockley, Dan Matronia, Alexander Savon
Next Milestone: | 1. Finalized Prototype 2. Team Site
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-03 | Testing | R | 2016-03-30 |  | Y | 2016-01-27
Design | Y | 2016-02-24 | Installation | R | 2015-04-13
Construction | Y | 2016-03-16
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | Y | Delivery to Scope |  | Y
Major Accomplishments/Decisions
This week we began the construction of our prototype. We have a rough draft built. The draft was built upon specifications from the Project Charter. We have built a sign in page, main page, location page, and other functionality in the prototype. We also made contact with out mentor as of last week. We are waiting on more direction from the mentor as of today.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Research & Analysis | Y | Design |  | 2016-01-27 | 2016-01-27 | Underway | 2016-02-03 | 2016-02-03
Project Plan | Y | Design |  | 2016-01-27 | 2016-01-27 | Assignment needed | 2016-02-10 | 2016-02-10
Project Charter | G | Design |  | 2016-01-20 | 2016-01-20 | Rough copy complete | 27- Jan
Role Assignment | G | Planning |  | 2016-01-27 | 2016-01-27 | complete | 27- jan | 2016-02-02
Prototype Building | Y | Design |  | 2016-02-02 | 2016-02-22 | Underway | 2016-04-06
G
G
G
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
The decision between an app or website |  | Y | We have decided to go with an smartphone application |  |  |  | Team
Creating the design of the product |  | Y | With little JIM experience, we need to figure out how this will function |  |  |  | Team
Planned Accomplishments
We have completed the majority of our research for the project; however, we need to be aware of changes in the industry and thus plan for that. Our main goal in the coming weeks is the completion/fine tuning of our prototype of the application.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.