## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date:
Project Name: | Find Your Fit | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Smartphone users seeking a certified fitness instructor within the area.
Project Core Team: | Nick Hockley, Dan Matronia, Alexander Savon
Next Milestone: | 1. Completion of design 2. Begin Prototyping
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | R | 2016-02-03 | Testing | Y | 2016-03-30
Design | Y | 2016-02-24 | Installation | Y | 2016-04-13
Construction | Y | 2016-03-16
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
This week we made a work breakdown structure to assign specific roles to each project member. This allows us to work independently during the week and bring our results to our group meetings on Wednesday.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Research and Analysis | Y | Design/Analysis |  | 2016-01-27 | 2016-01-27 | Need Additional Research | 2016-02-03 | N/A
Final Project Plan | Y | Design |  | 2016-01-27 | 2016-01-27 | Complete | 2016-02-10 | 2016-02-10
Final Project Charter | G | Design |  | 2016-01-27 | 2016-01-27 | Waiting on Feedback | 2016-02-10 | 2016-02-10
Role Assignment | G | Planning |  | 2016-01-27 | 2016-01-27 | Complete | 2016-01-27 | 2016-01-27
Prototype Design | R | Design |  | 2016-02-03 | 2016-02-03 |  | 2016-02-10 | N/A
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Creating the design of the prototype |  | R | We have to collectively sit down and draw our thoughts on the design in orde to discuss our thoughts. We have yet to do this step |  |  |  | Team
Starting JustInMind Prototyping |  | Y | We are supposed to start prototyping next week, |  |  |  | Dan
Planned Accomplishments
Next week we plan to have the final draft of our prototype design laid out. We will then begin working on the prototyping itself within the JustInMind software. .
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.