## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-09
Project Name: | FunishMe | [5 empty] | Project Status: | G
Project Description: | The project team will design, document, and prototype a mobile application that offers a one-stop solution to individuals looking to design and furnish their houses/apartments. Users will be able to: • Create their own designs and directly purchase the furniture they have selected through the application. • Connect with interior designers and collaborate with them in generating a desirable design through this application. • Sell and purchase second hand furniture through this platform.
Customer | The General Public
Project Core Team: | Carrie Graham, Yinping Hu, Anthony Minford, Mengxue Ni
Next Milestone: | Initial application design/prototyping
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Planning | G | 2016-01-28 | Construction | G | 2016-03-08
Analysis | G | 2016-02-02 | Testing | G | 2016-04-05
Design | Y | 2016-02-09 | Installation | G | 2016-04-19
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
The team has three major accomplishments for the period. 1) We created and finalized our project proposal. 2) We created our project charter, in addition to putting it through a revision. 3) We created our project site. Along with these accomplishments, we have also established a weekly meeting time and designated team roles.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Initial planning | G | Plan |  | 2016-01-28 | 2016-01-28 |  | 2016-02-02 | 2016-02-02
Prototype design | Y | Design |  | 2016-02-09 |  |  | 2016-03-08
--- User login | Y | Design |  | 2016-02-09 |  |  | 2016-03-08
--- Furnish function | Y | Design |  | 2016-02-09 |  |  | 2016-03-08
--- Furniture listing | Y | Design |  | 2016-02-09 |  |  | 2016-03-08
--- Shopping cart/checkout | Y | Design |  | 2016-02-09 |  |  | 2016-03-08
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Late on prototype design |  | Y | Part of designing will overlap with building the prototype to |  |  |  | Mengxue, Carrie
Carrie keeps on getting disconnected during online meetings |  | R | Switch to in-person meetings for the future |  |  |  | Carrie
Planned Accomplishments
This week we will start designing and building the initial layout of the application in Justinmind. We will also continue our weekly meetings to confirm progress on each member's part and ensure everything is in sync. We will also revise our charter by updating a few dates.
Note on B44: Key Issues are issues that need your CM Director-level understanding and awareness.