## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-02-01
Project Name: | Gamer Connect | [5 empty] | Project Status: | Y
Project Description: | Gamers across all platforms (Xbox, Playstation, and PC) have had trouble finding teams that match their skill level, and compliment their specific skill set. The various platforms do not offer a great way to meet new people and build teams based upon skill level. Gamebook will allow gamers to interact with each other and form teams based upon their respective skill levels. Gamebook will also give like-minded individuals a place to meet, interact, and compete.
Customer | Gamers
Project Core Team: | Andrew Fiss, Tyler Urquhart, Elijah Jamison, Kyle Domsohn
Next Milestone: | Complete rough draft of project plan and begin research
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2017-02-01 | Testing | R | 2017-03-31
Design | R | 2017-02-15 | Installation | R | 2017-04-12
Construction | R | 2017-02-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | R
Major Accomplishments/Decisions
Had first full group meeting. Discussed the scope of the project as well as our goals for the project. We discussed the preferred method for team communication and outlined each team mates responsibilities throughout the project. We completed first draft of project charter.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Refining Scope of Project | G | Analysis |  | 2005-02-01 | 2005-02-01 |  | 2005-02-15
Initial project plan | Y | Analysis |  | 2017-02-01 | 2017-02-01 |  | 2017-02-15
Research into market | R | Analysis |  | 2017-02-02 |  |  | 2017-02-15
Wire frame UI design | Y | Design |  | 2017-02-01 | 2017-02-01 |  | 2017-02-15
Research possible income streams | R | Analysis |  | 2017-02-01 | 2017-02-01 |  | 2017-02-15
Project schedule and Task assignment | Y | Analysis |  | 2005-02-01 | 2005-02-01 |  | 2017-02-08
Determine requirements and possible issues | R | Analysis |  | 2005-02-01 | 2005-02-01 |  | 2017-02-08
Prototype | R | Design |  | 2017-02-15 |  |  | 2017-03-31
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Project has yet to be approved |  | R | Get project approval |  |  |  | Team
Planned Accomplishments
Next week we plan to complete the project plan, continue to refine our scope, and begin wireframing the design our prototype. We will also seek to complete the analysis phase of our project within the next two weeks, and move fully into the design and construction phase of the project. We also hope to get project approval as soon as possible.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.