## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-03-29
Project Name: | Gamer Connect | [5 empty] | Project Status: | Y
Project Description: | Gamers across all platforms (Xbox, Playstation, and PC) have had trouble finding teams that match their skill level, and compliment their specific skill set. The various platforms do not offer a great way to meet new people and build teams based upon skill level. Gamebook will allow gamers to interact with each other and form teams based upon their respective skill levels. Gamebook will also give like-minded individuals a place to meet, interact, and compete.
Customer | Gamers
Project Core Team: | Andrew Fiss, Tyler Urquhart, Elijah Jamison, Kyle Domsohn
Next Milestone: | Complete first version of project Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-02-01 | Testing | Y | 2017-03-31
Design | G | 2017-02-15 | Installation | R | 2017-04-12
Construction | Y | 2017-02-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | R
Major Accomplishments/Decisions
Met with Shariq Khan for the second time on 3/24/17, and discussed the progress we have made since our first meeting a few weeks earlier. We are now near completion on the core aspects of the prototype, and are now in the process of reviewing the prototype and completing any detail work. Most of the project documentation, including the data model, process model, and systems architecture have a rough draft complete.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create Personas | R | Analysis |  | 2017-04-01 |  |  | 2017-04-05
Review project docs | G | Testing |  | 2017-02-15 | 2017-02-15 |  | 2017-04-21
Use Shariq's input to improve | Y | Analysis |  | 2017-03-06 | 2017-03-06 |  | 2017-04-21
Research possible income streams | Y | Analysis |  | 2017-02-01 | 2017-02-01 | Adding tournaments requires further analysis | 2017-02-15 | 2017-03-15
Financial Projections | R | Analysis |  | 2017-03-15 | 2017-03-25 |  | 2017-03-31
Project Site | R | Construction |  | 2017-03-15 |  |  | 2017-04-21
Prototype | Y | Design |  | 2017-02-15 | 2017-03-01 |  | 2017-03-31
Appendix Documents | Y | Construction |  | 2017-03-01 | 2017-03-20 |  | 2017-03-15
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Adjust charter and scope to reflect addition of tournament to our project |  | G | Met over past weekend and resolved most of the issues |  |  |  | Tyler and Kyle
Scheduling conflicts |  | Y | Utilize webex for meetings |  |  |  | Team
Some activities are running behind schedule |  | Y | Slack is in place in project schedule to mitigate small delays |  |  |  | Team
Planned Accomplishments
Next week we plan to continue work on the prototype and review all of our project documents in order to improve and refine each them. We will also start the project site and begin mapping out the layout in which we will upload project documents once finalized.
Note on B45: Key Issues are issues that need your CM Director-level understanding and awareness.