## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-04-19
Project Name: | Gamer Connect | [5 empty] | Project Status: | Y
Project Description: | Gamers across all platforms (Xbox, Playstation, and PC) have had trouble finding teams that match their skill level, and compliment their specific skill set. The various platforms do not offer a great way to meet new people and build teams based upon skill level. Gamebook will allow gamers to interact with each other and form teams based upon their respective skill levels. Gamebook will also give like-minded individuals a place to meet, interact, and compete.
Customer | Gamers
Project Core Team: | Andrew Fiss, Tyler Urquhart, Elijah Jamison, Kyle Domsohn
Next Milestone: | Refine all Final deliverables, Prepare for final presentation
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2017-02-01 | Testing | Y | 2017-03-31
Design | G | 2017-02-15 | Installation | Y | 2017-04-12
Construction | Y | 2017-02-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Met with our mentor to go over what he believe we should include and highlight in our final presentation. Refined our key documents and crafted our final presentation slide deck. Prepared for the dress rehearsal of our final project and brought the website very near completion.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Refine Final project deliverables | Y | Analysis |  | 2017-04-05 | 2017-04-10 |  | 2017-04-21
Refine and test Prototype | Y | Testing |  | 2017-04-05 | 2017-04-10 |  | 2017-04-21
Final Presentation Prep | Y | Testing |  | 2017-04-10 | 2017-04-14 |  | 2017-04-24
Complete website and uploads | Y | Construction |  | 2017-04-10 | 2017-04-14 |  | 2017-04-21
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Difficulties presenting Prototype |  | Y | Use webex to present if necessary; figure out alternative solution |  |  |  | Team
Planned Accomplishments
Over the next week we want to wrap up all aspects of the project and continue practice the final presentation. Try to meet on last time with Shariq to go over our final slide deck.
Note on B45: Key Issues are issues that need your CM Director-level understanding and awareness.