## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-11
Project Name: | Got your Back | [5 empty] | Project Status: | G
Project Description: | Our system, known as “Got Your Back,” utilizes Google Glass to solve one of the biggest dilemmas of today’s society: creating transparency between law enforcement and society while providing a new level of safety for police officers.
Customer | Philadelphia Police Force
Project Core Team: | Peter Hwang, Steve Scanlon, Ashley Lombardo, Jack Portnoy
Next Milestone: | Begin Prototyping
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-01-26 | Testing | Y | 2016-03-22
Design | G | 2016-02-23 | Installation | Y | 2016-04-05
Construction | G | 2016-03-08
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week we finalized what our project for the semester will be. Then we all met up together to finish our project charter.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create plan | G | Analysis |  | 2016-01-19 | 2005-02-01 |  | 2016-01-16 | 2016-01-16
Project Charter | G | Design |  | 2016-01-19 | 2016-02-01 |  | 2016-01-16 | 2016-01-16
Prototype | Y | Design |  | 2016-02-16 | 2016-02-16 |  | 2016-02-26 | 2016-02-26
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Only 1 prototyper |  | Y | Only one group member has experience prototyping a full project |  |  |  | Steve
Privacy issues |  | Y | We have to figure out privacy issues of officerswith glasses inside homes |  |  |  | All
Planned Accomplishments
Next week we plan on discussing as a group on how exactly we want our final product to look like so we can begin prototyping. We will continue our planning until our final design is complete.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.